## Instructions
Project Management Analytics — Practice Project
Excel project: Power Query · Excel Functions · PivotTables · Power Pivot (Data Model + DAX) · Dashboard
Scenario
You work as a Data Analyst supporting the PMO (Project Management Office) of a company running 15 parallel projects. Task-level data is exported from the old tracking tool and is messy: inconsistent text casing, extra spaces, mixed date formats, duplicate rows, and missing values. Your job is to clean the data, model it properly, build the analysis with formulas and PivotTables, then create a Power Pivot data model with DAX measures and present the results in a one-page interactive dashboard.
Workbook Contents
Instructions |  | This sheet — the full task brief and deliverables checklist.
Projects |  | Master list of 15 projects (source table for Power Query / Power Pivot).
Employees |  | Master list of staff with department and hourly rate (source table).
Tasks_RawData |  | Messy raw task export — the main table you will clean in Power Query.
PQ_Output (you create) |  | Destination sheet/table for your cleaned Power Query output.
PivotTables (you create) |  | Sheet(s) for your PivotTable analysis.
Dashboard (you create) |  | Final one-page interactive dashboard.
PART 1 — POWER QUERY (Data Cleaning & Shaping)
• | Import the Tasks_RawData table into Power Query (Data > Get Data > From Table/Range).
• | Remove exact duplicate rows.
• | Remove the 4 placeholder/test rows (Task_Name = "TEST - ignore").
• | Trim and Clean all text columns (remove leading/trailing/extra spaces).
• | Standardize the Department column to exactly: IT, Operations, Finance, Marketing, HR, Procurement, Quality Assurance (fix casing/abbreviations such as "it", "I.T", "Ops", "QA").
• | Standardize the Status column to exactly: Not Started, In Progress, Completed, Delayed (fix casing and synonyms such as "Pending", "Ongoing", "Done", "Behind Schedule").
• | Standardize the Priority column to exactly: High, Medium, Low (fix casing and single-letter codes H/M/L).
• | Convert Start_Date, Planned_End_Date and Actual_End_Date to a proper Date data type (the raw export mixes several date text formats).
• | Handle blanks: replace missing Planned_Cost / Actual_Cost with 0; replace missing Priority with "Not Set"; replace missing Assigned_To with "Unassigned".
• | Add a calculated column Planned_Duration_Days = Planned_End_Date − Start_Date.
• | Add a calculated column Delay_Days = Actual_End_Date − Planned_End_Date (blank/0 if not completed).
• | Merge (left outer join) with the Projects table on Project_ID to bring in Project_Manager, Client and Budget.
• | Merge (left outer join) with the Employees table on Assigned_To = Employee_Name to bring in Employee's Department (rename to Employee_Department) and Hourly_Rate.
• | Set correct data types on every column (text, whole number, decimal, date) before closing the query.
• | Load the cleaned result to a new sheet as an Excel Table named tbl_Tasks_Clean, AND load a copy to the Data Model (checkbox in the Load To dialog) for Part 4.
PART 2 — EXCEL FUNCTIONS
• | Work on your cleaned table (tbl_Tasks_Clean). Add the following helper columns using formulas (not hardcoded values):
• | Cost_Variance = Actual_Cost − Planned_Cost.
• | Cost_Variance_% = Cost_Variance / Planned_Cost, using IFERROR to handle any Planned_Cost = 0.
• | On_Time_Flag: use IF to return "On Time" when Status = "Completed" and Delay_Days <= 0, "Late" when Status = "Completed" and Delay_Days > 0, and "N/A" otherwise.
• | Task_Age_Category: use IFS (or nested IF) to bucket Planned_Duration_Days into "Short (<=7 days)", "Medium (8-20 days)", "Long (>20 days)".
• | Manager_Lookup: use INDEX/MATCH (not VLOOKUP) to pull Project_Manager from the Projects sheet by Project_ID, as a second, independent check on your Power Query merge.
• | Build a small Summary block (separate area of the same sheet or a new sheet) using:
• | • COUNTIFS — count of Delayed tasks per Department.
• | • SUMIFS — total Actual_Cost per Department for Completed tasks.
• | • AVERAGEIFS — average Delay_Days per Priority level, for Completed/Delayed tasks only.
• | • A TEXT + DATEDIF-based formula that produces a readable string such as "Delayed by 5 days" from Delay_Days.
PART 3 — PIVOTTABLES
• | Create a new sheet called PivotTables and build at least 4 PivotTables (or one PivotTable with multiple value fields, plus 3 focused ones) from tbl_Tasks_Clean:
• | 1) Total Planned_Cost vs Actual_Cost by Project_Name (rows = Project_Name, values = Sum of Planned_Cost & Actual_Cost).
• | 2) Count of tasks by Status, broken down by Department (rows = Department, columns = Status, values = Count of Task_ID).
• | 3) Average Delay_Days by Department and Priority (rows = Department, columns = Priority).
• | 4) Top 5 employees by total Actual_Cost of tasks assigned to them (use Value Filters > Top 10, set to 5).
• | Add at least one Slicer (e.g. on Status or Priority) connected to two of your PivotTables.
• | Format all value fields as currency where relevant and apply a PivotTable style consistent with the rest of the workbook.
PART 4 — POWER PIVOT (Data Model & DAX)
• | Open the Power Pivot window (Power Pivot tab > Manage Data Model). Confirm tbl_Tasks_Clean, Projects and Employees are all loaded to the Data Model.
• | Create relationships: Tasks_Clean[Project_ID] -> Projects[Project_ID], and Tasks_Clean[Assigned_To] -> Employees[Employee_Name].
• | Add the following DAX measures in the Data Model (name them exactly as shown):
• | • Total Planned Cost := SUM(Tasks_Clean[Planned_Cost])
• | • Total Actual Cost := SUM(Tasks_Clean[Actual_Cost])
• | • Cost Variance := [Total Actual Cost] - [Total Planned Cost]
• | • Cost Variance % := DIVIDE([Cost Variance], [Total Planned Cost], 0)
• | • Completed Tasks := CALCULATE(COUNTROWS(Tasks_Clean), Tasks_Clean[Status] = "Completed")
• | • On-Time Completion Rate := DIVIDE(CALCULATE(COUNTROWS(Tasks_Clean), Tasks_Clean[Status]="Completed", Tasks_Clean[Delay_Days]<=0), [Completed Tasks], 0)
• | • Average Delay Days := AVERAGEX(FILTER(Tasks_Clean, Tasks_Clean[Status]="Completed"), Tasks_Clean[Delay_Days])
• | Build a new PivotTable from the Data Model (not the plain range) using at least 3 of these measures, sliced by Project_Name and Department, to confirm the model works.
PART 5 — DASHBOARD
• | Create a new sheet called Dashboard, gridlines off, and lay out a single printable page (landscape).
• | Include at least 4 KPI cards driven by formulas/measures: Total Planned Cost, Total Actual Cost, Cost Variance %, On-Time Completion Rate.
• | Include at least 3 charts: (a) Column chart — Planned vs Actual Cost by Project, (b) Stacked bar/column — Task count by Status per Department, (c) Line or bar — Average Delay Days by Priority.
• | Include at least 2 slicers (e.g. Department and Priority) connected to the charts/PivotTables that drive the dashboard.
• | Use a consistent color palette and clear titles; the dashboard should read clearly without needing the raw data sheets.
Deliverable
Submit this single workbook with all sheets completed: Instructions (unchanged), Projects, Employees, Tasks_RawData (unchanged — keep as the original messy source), your Power Query output table, PivotTables sheet, the Power Pivot data model inside this file, and the Dashboard sheet.

## Summary
Department | Delayed_Task_Count | Completed_Actual_Cost | Priority | Avg_Delay_Completed | Avg_Delay_Delayed
IT | 7 | 72262 | High | 0.19231 | 5.2143
Operations | 3 | 77808 | Medium | -0.17647 | 5.8462
Finance | 0 | 0 | Low | -0.72222 | 2.3
Marketing | 0 | 0
HR | 0 | 0
Procurement | 6 | 53046
Quality Assurance | 0 | 0

## tbl_Projects
Project_ID | Project_Name | Client | Project_Manager | Start_Date | Budget
PRJ-001 | Website Redesign | Nile Corp | Mona Farid | 2024-06-12 | 75000
PRJ-002 | ERP System Rollout | Delta Retail Group | Youssef Adel | 2024-07-08 | 150000
PRJ-003 | Mobile App Launch | Alexandria Logistics | Ahmed Nabil | 2024-02-27 | 100000
PRJ-004 | Warehouse Automation | Cairo Financial Services | Laila Samir | 2024-06-22 | 75000
PRJ-005 | Customer Portal Upgrade | Horizon Manufacturing | Ahmed Nabil | 2024-01-09 | 50000
PRJ-006 | CRM Migration | BlueWave Telecom | Mona Farid | 2024-02-25 | 120000
PRJ-007 | Network Security Overhaul | Internal | Laila Samir | 2024-05-23 | 120000
PRJ-008 | Office Relocation | Pharos Holdings | Nourhan Tarek | 2024-02-26 | 300000
PRJ-009 | Supply Chain Optimization | Suez Trading Co. | Laila Samir | 2024-01-02 | 100000
PRJ-010 | Product Line Expansion | Internal | Sara Hassan | 2024-03-28 | 150000
PRJ-011 | HR System Implementation | Giza Health Systems | Ahmed Nabil | 2024-02-25 | 200000
PRJ-012 | Cloud Migration | Red Sea Tourism | Ahmed Nabil | 2024-01-24 | 250000
PRJ-013 | Brand Refresh Campaign | Internal | Nourhan Tarek | 2024-04-01 | 200000
PRJ-014 | Retail Store Opening | Orbit Media | Ahmed Nabil | 2024-01-12 | 300000
PRJ-015 | Data Center Upgrade | Internal | Nourhan Tarek | 2024-04-06 | 75000

## Projects
Project_ID | Project_Name | Client | Project_Manager | Start_Date | Budget
PRJ-001 | Website Redesign | Nile Corp | Mona Farid | 2024-06-12 | 75000
PRJ-002 | ERP System Rollout | Delta Retail Group | Youssef Adel | 2024-07-08 | 150000
PRJ-003 | Mobile App Launch | Alexandria Logistics | Ahmed Nabil | 2024-02-27 | 100000
PRJ-004 | Warehouse Automation | Cairo Financial Services | Laila Samir | 2024-06-22 | 75000
PRJ-005 | Customer Portal Upgrade | Horizon Manufacturing | Ahmed Nabil | 2024-01-09 | 50000
PRJ-006 | CRM Migration | BlueWave Telecom | Mona Farid | 2024-02-25 | 120000
PRJ-007 | Network Security Overhaul | Internal | Laila Samir | 2024-05-23 | 120000
PRJ-008 | Office Relocation | Pharos Holdings | Nourhan Tarek | 2024-02-26 | 300000
PRJ-009 | Supply Chain Optimization | Suez Trading Co. | Laila Samir | 2024-01-02 | 100000
PRJ-010 | Product Line Expansion | Internal | Sara Hassan | 2024-03-28 | 150000
PRJ-011 | HR System Implementation | Giza Health Systems | Ahmed Nabil | 2024-02-25 | 200000
PRJ-012 | Cloud Migration | Red Sea Tourism | Ahmed Nabil | 2024-01-24 | 250000
PRJ-013 | Brand Refresh Campaign | Internal | Nourhan Tarek | 2024-04-01 | 200000
PRJ-014 | Retail Store Opening | Orbit Media | Ahmed Nabil | 2024-01-12 | 300000
PRJ-015 | Data Center Upgrade | Internal | Nourhan Tarek | 2024-04-06 | 75000

## tbl_Employees
Employee_ID | Employee_Name | Department | Role | Hourly_Rate
EMP-001 | Hana Zaki | IT | Systems Analyst | 150
EMP-002 | Yasmin Younes | IT | Systems Analyst | 220
EMP-003 | Hassan Fouad | IT | Software Engineer | 280
EMP-004 | Tarek Abdelrahman | IT | IT Support Specialist | 180
EMP-005 | Dina Zaki | IT | Systems Analyst | 220
EMP-006 | Farida Younes | Operations | Operations Coordinator | 180
EMP-007 | Reem Gaber | Operations | Operations Coordinator | 180
EMP-008 | Sherif Hosny | Operations | Logistics Planner | 200
EMP-009 | Farida Zaki | Operations | Operations Coordinator | 200
EMP-010 | Yasmin Zaki | Operations | Logistics Planner | 220
EMP-011 | Khaled Naguib | Finance | Budget Controller | 250
EMP-012 | Khaled Younes | Finance | Accountant | 280
EMP-013 | Ziad Abdelrahman | Finance | Financial Analyst | 220
EMP-014 | Rania Gaber | Marketing | Brand Manager | 220
EMP-015 | Noor Naguib | Marketing | Content Strategist | 280
EMP-016 | Dina Fouad | Marketing | Marketing Specialist | 300
EMP-017 | Yasmin El-Sayed | HR | HR Generalist | 180
EMP-018 | Farida Hosny | HR | Training Coordinator | 150
EMP-019 | Fady Hosny | HR | Training Coordinator | 300
EMP-020 | Tarek Shawky | Procurement | Procurement Officer | 150
EMP-021 | Farida Shawky | Procurement | Vendor Manager | 250
EMP-022 | Mariam Kamal | Procurement | Vendor Manager | 180
EMP-023 | Sherif Ibrahim | Procurement | Vendor Manager | 180
EMP-024 | Mostafa El-Sayed | Procurement | Vendor Manager | 200
EMP-025 | Dina Mahmoud | Quality Assurance | QA Engineer | 250
EMP-026 | Aya Ibrahim | Quality Assurance | QA Engineer | 250
EMP-027 | Salma Fouad | Quality Assurance | QA Engineer | 200

## Employees
Employee_ID | Employee_Name | Department | Role | Hourly_Rate
EMP-001 | Hana Zaki | IT | Systems Analyst | 150
EMP-002 | Yasmin Younes | IT | Systems Analyst | 220
EMP-003 | Hassan Fouad | IT | Software Engineer | 280
EMP-004 | Tarek Abdelrahman | IT | IT Support Specialist | 180
EMP-005 | Dina Zaki | IT | Systems Analyst | 220
EMP-006 | Farida Younes | Operations | Operations Coordinator | 180
EMP-007 | Reem Gaber | Operations | Operations Coordinator | 180
EMP-008 | Sherif Hosny | Operations | Logistics Planner | 200
EMP-009 | Farida Zaki | Operations | Operations Coordinator | 200
EMP-010 | Yasmin Zaki | Operations | Logistics Planner | 220
EMP-011 | Khaled Naguib | Finance | Budget Controller | 250
EMP-012 | Khaled Younes | Finance | Accountant | 280
EMP-013 | Ziad Abdelrahman | Finance | Financial Analyst | 220
EMP-014 | Rania Gaber | Marketing | Brand Manager | 220
EMP-015 | Noor Naguib | Marketing | Content Strategist | 280
EMP-016 | Dina Fouad | Marketing | Marketing Specialist | 300
EMP-017 | Yasmin El-Sayed | HR | HR Generalist | 180
EMP-018 | Farida Hosny | HR | Training Coordinator | 150
EMP-019 | Fady Hosny | HR | Training Coordinator | 300
EMP-020 | Tarek Shawky | Procurement | Procurement Officer | 150
EMP-021 | Farida Shawky | Procurement | Vendor Manager | 250
EMP-022 | Mariam Kamal | Procurement | Vendor Manager | 180
EMP-023 | Sherif Ibrahim | Procurement | Vendor Manager | 180
EMP-024 | Mostafa El-Sayed | Procurement | Vendor Manager | 200
EMP-025 | Dina Mahmoud | Quality Assurance | QA Engineer | 250
EMP-026 | Aya Ibrahim | Quality Assurance | QA Engineer | 250
EMP-027 | Salma Fouad | Quality Assurance | QA Engineer | 200

## tbl_Tasks_Clean.
Task_ID | Project_ID | Project_Name | Task_Name | Department | Assigned_To | Priority | Status | Planned_Cost | Actual_Cost | Start_Date | Planned_End_Date | Actual_End_Date | Planned_Duration_Days | Delay_Days | Client | Project_Manager | Budget | Employee_Department | Hourly_Rate | Cost_Variance | Cost_Variance_% | On_Flag | Task_Age_Category | Manager_Lookup | Delay_Description
TSK-0085 | PRJ-004 | Warehouse Automation | Audit marketing collateral | Finance | Farida Hosny | Medium | Delayed | 1500 | 1396 | 2024-07-05 | 2024-08-02 | 2024-08-09 | 28 | 7 | Cairo Financial Services | Laila Samir | 75000 | HR | 150 | -104 | -6.933% | N/A | Long (>20 days) | Laila Samir | Delayed by 7 days
TSK-0014 | PRJ-001 | Website Redesign | Deploy inventory system | Operations | Farida Hosny | Medium | In Progress | 1500 | 618 | 2024-08-14 | 2024-09-07 |  | 24 | 0 | Nile Corp | Mona Farid | 75000 | HR | 150 | -882 | -58.8% | N/A | Long (>20 days) | Mona Farid | On schedule
TSK-0053 | PRJ-003 | Mobile App Launch | Migrate API integration | IT | Farida Hosny | Medium | Completed | 4000 | 5187 | 2024-06-07 | 2024-06-30 | 2024-06-27 | 23 | -3 | Alexandria Logistics | Ahmed Nabil | 100000 | HR | 150 | 1187 | 29.68% | On Time | Long (>20 days) | Ahmed Nabil | Early by 3 days
TSK-0082 | PRJ-004 | Warehouse Automation | Audit budget report | Marketing | Yasmin Younes | High | Done | 0 | 6098 | 2024-10-29 | 2024-11-03 | 2024-11-02 | 5 | -1 | Cairo Financial Services | Laila Samir | 75000 | IT | 220 | 6098 | 0% | N/A | Short (<=7 days) | Laila Samir | Early by 1 days
TSK-0276 | PRJ-014 | Retail Store Opening | Develop backup procedure | Operations | Noor Naguib | High | In Progress | 4000 | 1731 | 2024-05-23 | 2024-06-20 |  | 28 | 0 | Orbit Media | Ahmed Nabil | 300000 | Marketing | 280 | -2269 | -56.73% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0104 | PRJ-005 | Customer Portal Upgrade | Install budget report | Finance | Noor Naguib | Low | Completed | 2000 | 2594 |  |  |  |  | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | Marketing | 280 | 594 | 29.7% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0192 | PRJ-010 | Product Line Expansion | Analyze security policy | IT | Noor Naguib | Medium | Not Started | 8000 | 0 | 2024-06-19 | 2024-06-24 |  | 5 | 0 | Internal | Sara Hassan | 150000 | Marketing | 280 | -8000 | -100% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0245 | PRJ-012 | Cloud Migration | Test marketing collateral | Marketing | Noor Naguib | Low | Completed | 1500 | 1982 | 2024-02-26 | 2024-03-15 | 2024-03-15 | 18 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Marketing | 280 | 482 | 32.13% | On Time | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0153 | PRJ-008 | Office Relocation | Audit inventory system |  | Hassan Fouad | Medium | Ongoing | 10000 | 5964 | 2024-04-13 | 2024-05-07 |  | 24 | 0 | Pharos Holdings | Nourhan Tarek | 300000 | IT | 280 | -4036 | -40.36% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0288 | PRJ-014 | Retail Store Opening | Optimize customer feedback survey | IT | Salma Fouad | Low | Completed | 1000 | 1263 |  |  |  |  | 0 | Orbit Media | Ahmed Nabil | 300000 | Quality Assurance | 200 | 263 | 26.3% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0204 | PRJ-010 | Product Line Expansion | Document warehouse layout | IT | Salma Fouad | High | Done | 2500 | 2216 | 2024-04-22 | 2024-05-02 | 2024-05-04 | 10 | 2 | Internal | Sara Hassan | 150000 | Quality Assurance | 200 | -284 | -11.36% | N/A | Medium (8-20 days) | Sara Hassan | Delayed by 2 days
TSK-0211 | PRJ-011 | HR System Implementation | Document training material | IT | Tarek Abdelrahman | High | In Progress | 4000 | 2110 | 2024-06-30 | 2024-07-15 |  | 15 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | IT | 180 | -1890 | -47.25% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0038 | PRJ-002 | ERP System Rollout | Audit API integration | Procurement | Tarek Abdelrahman | High | Not Started | 6000 | 0 | 2024-08-09 | 2024-09-01 |  | 23 | 0 | Delta Retail Group | Youssef Adel | 150000 | IT | 180 | -6000 | -100% | N/A | Long (>20 days) | Youssef Adel | On schedule
TSK-0216 | PRJ-011 | HR System Implementation | Procure warehouse layout | Marketing | Khaled Younes | Low | In Progress | 1500 | 377 | 2024-04-03 | 2024-04-30 |  | 27 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Finance | 280 | -1123 | -74.87% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0093 | PRJ-005 | Customer Portal Upgrade | Procure vendor contract | Marketing | Dina Zaki | Medium | Completed | 0 | 2553 | 2024-01-10 | 2024-01-15 | 2024-01-12 | 5 | -3 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 220 | 2553 | 0% | On Time | Short (<=7 days) | Ahmed Nabil | Early by 3 days
TSK-0212 | PRJ-011 | HR System Implementation | Test backup procedure | IT | Farida Younes | High | Not Started | 5000 | 0 | 2024-05-22 | 2024-05-30 |  | 8 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Operations | 180 | -5000 | -100% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0058 | PRJ-003 | Mobile App Launch | Audit inventory system |  | Tarek Shawky | Medium | Not Started | 1000 | 0 | 2024-07-20 | 2024-08-19 |  | 30 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Procurement | 150 | -1000 | -100% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0213 | PRJ-011 | HR System Implementation | Train users on hardware setup | Marketing | Reem Gaber | Low | In Progress | 1500 | 598 | 2024-04-05 | 2024-04-09 |  | 4 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Operations | 180 | -902 | -60.13% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0024 | PRJ-002 | ERP System Rollout | Migrate backup procedure | Finance | Sherif Hosny | Low | Completed | 1500 | 1799 | 2024-09-07 | 2024-09-18 | 2024-09-18 | 11 | 0 | Delta Retail Group | Youssef Adel | 150000 | Operations | 200 | 299 | 19.93% | On Time | Medium (8-20 days) | Youssef Adel | On schedule
TSK-0122 | PRJ-006 | CRM Migration | Audit vendor contract | Finance | Aya Ibrahim | Medium | Delayed | 4000 | 4369 | 2024-06-29 | 2024-07-12 | 2024-07-24 | 13 | 12 | BlueWave Telecom | Mona Farid | 120000 | Quality Assurance | 250 | 369 | 9.225% | N/A | Medium (8-20 days) | Mona Farid | Delayed by 12 days
TSK-0101 | PRJ-005 | Customer Portal Upgrade | Design network infrastructure | Quality | Aya Ibrahim | Medium | Completed | 5000 | 4772 |  |  |  |  | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | Quality Assurance | 250 | -228 | -4.56% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0090 | PRJ-005 | Customer Portal Upgrade | Optimize quality checklist | Marketing | Farida Zaki | Low | Completed | 10000 | 7969 | 2024-02-19 | 2024-03-19 | 2024-03-17 | 29 | -2 | Horizon Manufacturing | Ahmed Nabil | 50000 | Operations | 200 | -2031 | -20.31% | On Time | Long (>20 days) | Ahmed Nabil | Early by 2 days
TSK-0299 | PRJ-015 | Data Center Upgrade | Configure supplier list | Finance | Dina Fouad | High | In Progress | 4000 | 1678 | 2024-08-04 | 2024-08-26 |  | 22 | 0 | Internal | Nourhan Tarek | 75000 | Marketing | 300 | -2322 | -58.05% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0303 | PRJ-015 | Data Center Upgrade | Plan hardware setup | Finance | Farida Shawky | Medium | Not Started | 10000 | 0 | 2024-05-26 | 2024-06-16 |  | 21 | 0 | Internal | Nourhan Tarek | 75000 | Procurement | 250 | -10000 | -100% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0172 | PRJ-009 | Supply Chain Optimization | Audit user interface | Quality | Farida Shawky | Low | Completed | 1500 | 1823 |  |  |  |  | 0 | Suez Trading Co. | Laila Samir | 100000 | Procurement | 250 | 323 | 21.53% | On Time | Short (<=7 days) | Laila Samir | On schedule
TSK-0150 | PRJ-008 | Office Relocation | Develop training material | Finance | Mariam Kamal | High | Delayed | 1000 | 1347 | 2024-07-20 | 2024-08-07 | 2024-08-12 | 18 | 5 | Pharos Holdings | Nourhan Tarek | 300000 | Procurement | 180 | 347 | 34.7% | N/A | Medium (8-20 days) | Nourhan Tarek | Delayed by 5 days
TSK-0149 | PRJ-008 | Office Relocation | Test API integration | Quality | Sherif Ibrahim | Medium | Not Started | 1000 | 0 |  |  |  |  | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Procurement | 180 | -1000 | -100% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0198 | PRJ-010 | Product Line Expansion | Plan database schema | IT | Unassigned | High | Completed | 8000 | 5874 | 2024-05-30 | 2024-06-13 | 2024-06-13 | 14 | 0 | Internal | Sara Hassan | 150000 |  |  | -2126 | -26.57% | On Time | Medium (8-20 days) | Sara Hassan | On schedule
TSK-0119 | PRJ-006 | CRM Migration | Document user interface | Quality | Ziad Abdelrahman | Medium | Done | 10000 | 12422 |  |  |  |  | 0 | BlueWave Telecom | Mona Farid | 120000 | Finance | 220 | 2422 | 24.22% | N/A | Short (<=7 days) | Mona Farid | On schedule
TSK-0304 | PRJ-015 | Data Center Upgrade | Approve budget report | Marketing | Khaled Naguib | Low | Delayed | 2000 | 2297 | 2024-08-02 | 2024-08-25 | 2024-08-26 | 23 | 1 | Internal | Nourhan Tarek | 75000 | Finance | 250 | 297 | 14.85% | N/A | Long (>20 days) | Nourhan Tarek | Delayed by 1 days
TSK-0048 | PRJ-003 | Mobile App Launch | Install vendor contract | IT | Salma Fouad | Medium | Completed | 1500 | 1286 | 2024-03-01 | 2024-03-21 | 2024-03-21 | 20 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Quality Assurance | 200 | -214 | -14.27% | On Time | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0051 | PRJ-003 | Mobile App Launch | Approve onboarding process | HR | Mostafa El-Sayed | High | Completed | 5000 | 3653 | 2024-07-22 | 2024-08-06 | 2024-08-04 | 15 | -2 | Alexandria Logistics | Ahmed Nabil | 100000 | Procurement | 200 | -1347 | -26.94% | On Time | Medium (8-20 days) | Ahmed Nabil | Early by 2 days
TSK-0068 | PRJ-004 | Warehouse Automation | Review API integration | IT | Ziad Abdelrahman | High | Done | 1000 | 1399 | 2024-10-17 | 2024-11-09 | 2024-11-06 | 23 | -3 | Cairo Financial Services | Laila Samir | 75000 | Finance | 220 | 399 | 39.9% | N/A | Long (>20 days) | Laila Samir | Early by 3 days
TSK-0307 | PRJ-015 | Data Center Upgrade | Deploy server configuration | IT | Noor Naguib | High | In Progress | 2500 | 1606 |  |  |  |  | 0 | Internal | Nourhan Tarek | 75000 | Marketing | 280 | -894 | -35.76% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0017 | PRJ-001 | Website Redesign | Procure customer feedback survey | HR | Khaled Younes | Medium | Delayed | 1500 | 1676 | 2024-11-07 | 2024-11-18 | 2024-11-16 | 11 | -2 | Nile Corp | Mona Farid | 75000 | Finance | 280 | 176 | 11.73% | N/A | Medium (8-20 days) | Mona Farid | Early by 2 days
TSK-0206 | PRJ-010 | Product Line Expansion | Configure network infrastructure | IT | Khaled Naguib | High | Pending | 1000 | 0 | 2024-08-09 | 2024-08-27 |  | 18 | 0 | Internal | Sara Hassan | 150000 | Finance | 250 | -1000 | -100% | N/A | Medium (8-20 days) | Sara Hassan | On schedule
TSK-0117 | PRJ-006 | CRM Migration | Migrate server configuration | Marketing | Tarek Shawky | High | Pending | 5000 | 0 | 2024-05-16 | 2024-05-24 |  | 8 | 0 | BlueWave Telecom | Mona Farid | 120000 | Procurement | 150 | -5000 | -100% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0108 | PRJ-006 | CRM Migration | Deploy hardware setup | Operations | Farida Hosny | Medium | Delayed | 3000 | 2512 | 2024-05-07 | 2024-06-06 | 2024-06-05 | 30 | -1 | BlueWave Telecom | Mona Farid | 120000 | HR | 150 | -488 | -16.27% | N/A | Long (>20 days) | Mona Farid | Early by 1 days
TSK-0196 | PRJ-010 | Product Line Expansion | Review network infrastructure | Operations | Reem Gaber | Medium | In Progress | 3000 | 1021 |  |  |  |  | 0 | Internal | Sara Hassan | 150000 | Operations | 180 | -1979 | -65.97% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0305 | PRJ-015 | Data Center Upgrade | Plan training material | Finance | Noor Naguib | Low | Completed | 10000 | 10647 | 2024-06-14 | 2024-07-01 | 2024-06-30 | 17 | -1 | Internal | Nourhan Tarek | 75000 | Marketing | 280 | 647 | 6.47% | On Time | Medium (8-20 days) | Nourhan Tarek | Early by 1 days
TSK-0177 | PRJ-009 | Supply Chain Optimization | Migrate employee handbook | Procurement | Khaled Naguib | Low | In Progress | 2500 | 1242 | 2024-02-26 | 2024-03-13 |  | 16 | 0 | Suez Trading Co. | Laila Samir | 100000 | Finance | 250 | -1258 | -50.32% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0137 | PRJ-007 | Network Security Overhaul | Develop inventory system | IT | Noor Naguib | Low | Completed | 1500 | 1674 | 2024-07-23 | 2024-08-01 | 2024-07-29 | 9 | -3 | Internal | Laila Samir | 120000 | Marketing | 280 | 174 | 11.6% | On Time | Medium (8-20 days) | Laila Samir | Early by 3 days
TSK-0210 | PRJ-011 | HR System Implementation | Analyze marketing collateral | Finance | Sherif Hosny | High | In Progress | 1000 | 359 | 2024-05-20 | 2024-06-06 |  | 17 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Operations | 200 | -641 | -64.1% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0181 | PRJ-009 | Supply Chain Optimization | Deploy budget report | Operations | Ziad Abdelrahman | High | Not Started | 2000 | 0 |  |  |  |  | 0 | Suez Trading Co. | Laila Samir | 100000 | Finance | 220 | -2000 | -100% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0176 | PRJ-009 | Supply Chain Optimization | Design budget report | Marketing | Khaled Naguib | Medium | Completed | 6000 | 8191 | 2024-03-13 | 2024-04-07 | 2024-04-06 | 25 | -1 | Suez Trading Co. | Laila Samir | 100000 | Finance | 250 | 2191 | 36.52% | On Time | Long (>20 days) | Laila Samir | Early by 1 days
TSK-0189 | PRJ-010 | Product Line Expansion | Plan quality checklist | HR | Dina Fouad | Low | Ongoing | 8000 | 3329 | 2024-08-02 | 2024-08-19 |  | 17 | 0 | Internal | Sara Hassan | 150000 | Marketing | 300 | -4671 | -58.39% | N/A | Medium (8-20 days) | Sara Hassan | On schedule
TSK-0138 | PRJ-007 | Network Security Overhaul | Document hardware setup | Operations | Tarek Shawky | High | In Progress | 10000 | 3913 | 2024-07-21 | 2024-08-19 |  | 29 | 0 | Internal | Laila Samir | 120000 | Procurement | 150 | -6087 | -60.87% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0061 | PRJ-003 | Mobile App Launch | Approve quality checklist | Quality | Khaled Younes | Medium | Behind Schedule | 8000 | 6292 | 2024-06-07 | 2024-06-10 | 2024-06-15 | 3 | 5 | Alexandria Logistics | Ahmed Nabil | 100000 | Finance | 280 | -1708 | -21.35% | N/A | Short (<=7 days) | Ahmed Nabil | Delayed by 5 days
TSK-0067 | PRJ-004 | Warehouse Automation | Optimize dashboard | HR | Mostafa El-Sayed | High | Not Started | 1500 | 0 | 2024-10-07 | 2024-10-26 |  | 19 | 0 | Cairo Financial Services | Laila Samir | 75000 | Procurement | 200 | -1500 | -100% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0088 | PRJ-005 | Customer Portal Upgrade | Plan customer feedback survey | Finance | Dina Zaki | Low | Done | 2000 | 2236 |  |  |  |  | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 220 | 236 | 11.8% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0037 | PRJ-002 | ERP System Rollout | Audit inventory system | Procurement | Salma Fouad | Medium | In Progress | 3000 | 2365 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Quality Assurance | 200 | -635 | -21.17% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0266 | PRJ-013 | Brand Refresh Campaign | Review employee handbook | Operations | Hana Zaki | High | Done | 5000 | 5016 | 2024-07-14 | 2024-07-29 | 2024-07-29 | 15 | 0 | Internal | Nourhan Tarek | 200000 | IT | 150 | 16 | 0.32% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0070 | PRJ-004 | Warehouse Automation | Procure vendor contract | Quality | Noor Naguib | Low | Behind Schedule | 5000 | 4686 | 2024-10-10 | 2024-10-27 | 2024-10-31 | 17 | 4 | Cairo Financial Services | Laila Samir | 75000 | Marketing | 280 | -314 | -6.28% | N/A | Medium (8-20 days) | Laila Samir | Delayed by 4 days
TSK-0205 | PRJ-010 | Product Line Expansion | Configure API integration | Finance | Fady Hosny | Medium | Ongoing | 4000 | 3074 |  |  |  |  | 0 | Internal | Sara Hassan | 150000 | HR | 300 | -926 | -23.15% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0263 | PRJ-013 | Brand Refresh Campaign | Train users on employee handbook | IT | Tarek Abdelrahman | High | Completed | 5000 | 6706 | 2024-04-11 | 2024-05-05 | 2024-05-04 | 24 | -1 | Internal | Nourhan Tarek | 200000 | IT | 180 | 1706 | 34.12% | On Time | Long (>20 days) | Nourhan Tarek | Early by 1 days
TSK-0248 | PRJ-012 | Cloud Migration | Review onboarding process | Operations | Mostafa El-Sayed | Medium | Done | 1500 | 2080 | 2024-05-30 | 2024-06-16 | 2024-06-15 | 17 | -1 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 200 | 580 | 38.67% | N/A | Medium (8-20 days) | Ahmed Nabil | Early by 1 days
TSK-0044 | PRJ-003 | Mobile App Launch | Design marketing collateral | HR | Sherif Hosny | High | Ongoing | 3000 | 647 | 2024-05-19 | 2024-06-10 |  | 22 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Operations | 200 | -2353 | -78.43% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0208 | PRJ-011 | HR System Implementation | Document warehouse layout | Operations | Tarek Shawky | Low | Completed | 8000 | 9484 | 2024-05-16 | 2024-05-24 | 2024-05-26 | 8 | 2 | Giza Health Systems | Ahmed Nabil | 200000 | Procurement | 150 | 1484 | 18.55% | Late | Medium (8-20 days) | Ahmed Nabil | Delayed by 2 days
TSK-0277 | PRJ-014 | Retail Store Opening | Train users on onboarding process | Procurement | Salma Fouad | Low | Completed | 4000 | 4446 | 2024-04-17 | 2024-05-10 | 2024-05-10 | 23 | 0 | Orbit Media | Ahmed Nabil | 300000 | Quality Assurance | 200 | 446 | 11.15% | On Time | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0291 | PRJ-014 | Retail Store Opening | Analyze quality checklist | Finance | Salma Fouad | Low | In Progress | 8000 | 2966 | 2024-01-29 | 2024-02-03 |  | 5 | 0 | Orbit Media | Ahmed Nabil | 300000 | Quality Assurance | 200 | -5034 | -62.92% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0076 | PRJ-004 | Warehouse Automation | Optimize server configuration | Marketing | Tarek Abdelrahman | Medium | Completed | 1500 | 1412 | 2024-08-16 | 2024-09-12 | 2024-09-13 | 27 | 1 | Cairo Financial Services | Laila Samir | 75000 | IT | 180 | -88 | -5.867% | Late | Long (>20 days) | Laila Samir | Delayed by 1 days
TSK-0284 | PRJ-014 | Retail Store Opening | Document budget report | Marketing | Farida Zaki | Medium | Delayed | 1500 | 1497 | 2024-06-10 | 2024-07-08 | 2024-07-23 | 28 | 15 | Orbit Media | Ahmed Nabil | 300000 | Operations | 200 | -3 | -0.2% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 15 days
TSK-0297 | PRJ-015 | Data Center Upgrade | Deploy user interface | Finance | Dina Mahmoud | Medium | Done | 3000 | 2936 | 2024-05-22 | 2024-06-18 | 2024-06-19 | 27 | 1 | Internal | Nourhan Tarek | 75000 | Quality Assurance | 250 | -64 | -2.133% | N/A | Long (>20 days) | Nourhan Tarek | Delayed by 1 days
TSK-0259 | PRJ-013 | Brand Refresh Campaign | Plan server configuration | Quality | Hassan Fouad | Low | Completed | 2000 | 2777 |  |  |  |  | 0 | Internal | Nourhan Tarek | 200000 | IT | 280 | 777 | 38.85% | On Time | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0006 | PRJ-001 | Website Redesign | Design onboarding process | HR | Farida Younes | High | Delayed | 5000 | 6659 | 2024-10-14 | 2024-11-01 | 2024-11-04 | 18 | 3 | Nile Corp | Mona Farid | 75000 | Operations | 180 | 1659 | 33.18% | N/A | Medium (8-20 days) | Mona Farid | Delayed by 3 days
TSK-0296 | PRJ-015 | Data Center Upgrade | Design employee handbook | Finance | Hassan Fouad | Low | In Progress | 1500 | 408 | 2024-05-15 | 2024-06-11 |  | 27 | 0 | Internal | Nourhan Tarek | 75000 | IT | 280 | -1092 | -72.8% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0007 | PRJ-001 | Website Redesign | Develop backup procedure | Marketing | Unassigned | Low | Ongoing | 3000 | 992 | 2024-07-21 | 2024-07-30 |  | 9 | 0 | Nile Corp | Mona Farid | 75000 |  |  | -2008 | -66.93% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0271 | PRJ-014 | Retail Store Opening | Deploy warehouse layout | Finance | Tarek Shawky | High | Completed | 6000 | 6093 | 2024-01-29 | 2024-02-07 | 2024-02-06 | 9 | -1 | Orbit Media | Ahmed Nabil | 300000 | Procurement | 150 | 93 | 1.55% | On Time | Medium (8-20 days) | Ahmed Nabil | Early by 1 days
TSK-0252 | PRJ-013 | Brand Refresh Campaign | Procure warehouse layout | Procurement | Yasmin Younes | Medium | Completed | 1000 | 1071 | 2024-08-08 | 2024-08-15 | 2024-08-15 | 7 | 0 | Internal | Nourhan Tarek | 200000 | IT | 220 | 71 | 7.1% | On Time | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0222 | PRJ-011 | HR System Implementation | Test security policy | Finance | Rania Gaber | High | Delayed | 4000 | 3554 | 2024-05-11 | 2024-06-06 | 2024-06-17 | 26 | 11 | Giza Health Systems | Ahmed Nabil | 200000 | Marketing | 220 | -446 | -11.15% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 11 days
TSK-0201 | PRJ-010 | Product Line Expansion | Train users on dashboard | HR | Farida Younes | Medium | Completed | 2000 | 1896 | 2024-07-03 | 2024-07-27 | 2024-07-27 | 24 | 0 | Internal | Sara Hassan | 150000 | Operations | 180 | -104 | -5.2% | On Time | Long (>20 days) | Sara Hassan | On schedule
TSK-0207 | PRJ-010 | Product Line Expansion | Analyze onboarding process | Quality | Khaled Younes | Low | Not Started | 8000 | 0 | 2024-04-25 | 2024-05-25 |  | 30 | 0 | Internal | Sara Hassan | 150000 | Finance | 280 | -8000 | -100% | N/A | Long (>20 days) | Sara Hassan | On schedule
TSK-0185 | PRJ-009 | Supply Chain Optimization | Develop onboarding process |  | Reem Gaber | Medium | In Progress | 1500 | 312 | 2024-01-06 | 2024-01-27 |  | 21 | 0 | Suez Trading Co. | Laila Samir | 100000 | Operations | 180 | -1188 | -79.2% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0045 | PRJ-003 | Mobile App Launch | Procure backup procedure | Operations | Dina Fouad | Medium | Completed | 6000 | 8270 | 2024-07-25 | 2024-08-10 | 2024-08-12 | 16 | 2 | Alexandria Logistics | Ahmed Nabil | 100000 | Marketing | 300 | 2270 | 37.83% | Late | Medium (8-20 days) | Ahmed Nabil | Delayed by 2 days
TSK-0218 | PRJ-011 | HR System Implementation | Train users on backup procedure | Operations | Farida Shawky | High | Completed | 2500 | 3495 |  |  |  |  | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Procurement | 250 | 995 | 39.8% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0190 | PRJ-010 | Product Line Expansion | Plan user interface | HR | Ziad Abdelrahman | High | Ongoing | 1000 | 483 |  |  |  |  | 0 | Internal | Sara Hassan | 150000 | Finance | 220 | -517 | -51.7% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0295 | PRJ-015 | Data Center Upgrade | Optimize security policy | Finance | Mostafa El-Sayed | Medium | Completed | 3000 | 2484 |  |  |  |  | 0 | Internal | Nourhan Tarek | 75000 | Procurement | 200 | -516 | -17.2% | On Time | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0155 | PRJ-008 | Office Relocation | Approve database schema | Marketing | Tarek Shawky | Medium | Done | 8000 | 6121 | 2024-03-03 | 2024-03-08 | 2024-03-07 | 5 | -1 | Pharos Holdings | Nourhan Tarek | 300000 | Procurement | 150 | -1879 | -23.49% | N/A | Short (<=7 days) | Nourhan Tarek | Early by 1 days
TSK-0109 | PRJ-006 | CRM Migration | Develop warehouse layout | Procurement | Hana Zaki | High | Done | 1000 | 1278 | 2024-05-21 | 2024-06-19 | 2024-06-20 | 29 | 1 | BlueWave Telecom | Mona Farid | 120000 | IT | 150 | 278 | 27.8% | N/A | Long (>20 days) | Mona Farid | Delayed by 1 days
TSK-0281 | PRJ-014 | Retail Store Opening | Plan backup procedure | HR | Yasmin El-Sayed | High | Delayed | 2000 | 2272 | 2024-02-17 | 2024-03-16 | 2024-03-31 | 28 | 15 | Orbit Media | Ahmed Nabil | 300000 | HR | 180 | 272 | 13.6% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 15 days
TSK-0144 | PRJ-007 | Network Security Overhaul | Approve warehouse layout | Operations | Khaled Naguib | Low | Pending | 2500 | 0 |  |  |  |  | 0 | Internal | Laila Samir | 120000 | Finance | 250 | -2500 | -100% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0077 | PRJ-004 | Warehouse Automation | Optimize supplier list | Marketing | Tarek Abdelrahman | High | Not Started | 4000 | 0 | 2024-08-26 | 2024-09-07 |  | 12 | 0 | Cairo Financial Services | Laila Samir | 75000 | IT | 180 | -4000 | -100% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0124 | PRJ-006 | CRM Migration | Develop vendor contract | HR | Sherif Hosny | Low | Pending | 8000 | 0 |  |  |  |  | 0 | BlueWave Telecom | Mona Farid | 120000 | Operations | 200 | -8000 | -100% | N/A | Short (<=7 days) | Mona Farid | On schedule
TSK-0285 | PRJ-014 | Retail Store Opening | Procure quality checklist | Marketing | Sherif Ibrahim | Low | In Progress | 5000 | 2964 | 2024-05-24 | 2024-05-27 |  | 3 | 0 | Orbit Media | Ahmed Nabil | 300000 | Procurement | 180 | -2036 | -40.72% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0063 | PRJ-003 | Mobile App Launch | Deploy supplier list | Marketing | Unassigned | High | Pending | 8000 | 0 | 2024-06-22 | 2024-07-06 |  | 14 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 |  |  | -8000 | -100% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0023 | PRJ-002 | ERP System Rollout | Install training material | IT | Rania Gaber | Low | Not Started | 8000 | 0 | 2024-10-29 | 2024-11-20 |  | 22 | 0 | Delta Retail Group | Youssef Adel | 150000 | Marketing | 220 | -8000 | -100% | N/A | Long (>20 days) | Youssef Adel | On schedule
TSK-0253 | PRJ-013 | Brand Refresh Campaign | Train users on onboarding process | Operations | Tarek Shawky | High | In Progress | 5000 | 2256 |  |  |  |  | 0 | Internal | Nourhan Tarek | 200000 | Procurement | 150 | -2744 | -54.88% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0042 | PRJ-003 | Mobile App Launch | Configure supplier list | Finance | Aya Ibrahim | Low | In Progress | 2500 | 1886 | 2024-03-16 | 2024-04-09 |  | 24 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Quality Assurance | 250 | -614 | -24.56% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0261 | PRJ-013 | Brand Refresh Campaign | Test server configuration | HR | Farida Younes | Low | Done | 4000 | 4271 | 2024-04-19 | 2024-05-17 | 2024-05-19 | 28 | 2 | Internal | Nourhan Tarek | 200000 | Operations | 180 | 271 | 6.775% | N/A | Long (>20 days) | Nourhan Tarek | Delayed by 2 days
TSK-0229 | PRJ-011 | HR System Implementation | Optimize hardware setup | Procurement | Mostafa El-Sayed | High | Ongoing | 4000 | 2434 | 2024-06-07 | 2024-07-01 |  | 24 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Procurement | 200 | -1566 | -39.15% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0132 | PRJ-007 | Network Security Overhaul | Deploy training material | Marketing | Fady Hosny | High | Pending | 2500 | 0 | 2024-10-10 | 2024-10-29 |  | 19 | 0 | Internal | Laila Samir | 120000 | HR | 300 | -2500 | -100% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0270 | PRJ-013 | Brand Refresh Campaign | Train users on vendor contract | Finance | Mariam Kamal | High | Pending | 3000 | 0 | 2024-08-19 | 2024-08-24 |  | 5 | 0 | Internal | Nourhan Tarek | 200000 | Procurement | 180 | -3000 | -100% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0112 | PRJ-006 | CRM Migration | Procure inventory system |  | Ziad Abdelrahman | High | Not Started | 3000 | 0 | 2024-03-20 | 2024-03-24 |  | 4 | 0 | BlueWave Telecom | Mona Farid | 120000 | Finance | 220 | -3000 | -100% | N/A | Short (<=7 days) | Mona Farid | On schedule
TSK-0237 | PRJ-012 | Cloud Migration | Plan vendor contract | Quality | Hana Zaki | High | In Progress | 2000 | 653 | 2024-03-21 | 2024-04-16 |  | 26 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | IT | 150 | -1347 | -67.35% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0127 | PRJ-007 | Network Security Overhaul | Migrate training material | Finance | Unassigned | Low | Done | 6000 | 5346 | 2024-06-26 | 2024-07-26 | 2024-07-27 | 30 | 1 | Internal | Laila Samir | 120000 |  |  | -654 | -10.9% | N/A | Long (>20 days) | Laila Samir | Delayed by 1 days
TSK-0257 | PRJ-013 | Brand Refresh Campaign | Document employee handbook | Quality | Mostafa El-Sayed | High | Ongoing | 10000 | 7208 | 2024-07-25 | 2024-07-31 |  | 6 | 0 | Internal | Nourhan Tarek | 200000 | Procurement | 200 | -2792 | -27.92% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0030 | PRJ-002 | ERP System Rollout | Plan hardware setup | Procurement | Sherif Ibrahim | Medium | Completed | 10000 | 13746 | 2024-10-10 | 2024-10-18 | 2024-10-19 | 8 | 1 | Delta Retail Group | Youssef Adel | 150000 | Procurement | 180 | 3746 | 37.46% | Late | Medium (8-20 days) | Youssef Adel | Delayed by 1 days
TSK-0032 | PRJ-002 | ERP System Rollout | Train users on customer feedback survey | IT | Rania Gaber | Medium | Completed | 6000 | 7171 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Marketing | 220 | 1171 | 19.52% | On Time | Short (<=7 days) | Youssef Adel | On schedule
TSK-0075 | PRJ-004 | Warehouse Automation | Plan customer feedback survey | Marketing | Yasmin Younes | Medium | Completed | 10000 | 7595 |  |  |  |  | 0 | Cairo Financial Services | Laila Samir | 75000 | IT | 220 | -2405 | -24.05% | On Time | Short (<=7 days) | Laila Samir | On schedule
TSK-0159 | PRJ-008 | Office Relocation | Design dashboard | HR | Farida Hosny | Medium | In Progress | 2500 | 1388 |  |  |  |  | 0 | Pharos Holdings | Nourhan Tarek | 300000 | HR | 150 | -1112 | -44.48% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0235 | PRJ-012 | Cloud Migration | Document quality checklist | IT | Farida Shawky | High | In Progress | 1000 | 606 |  |  |  |  | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 250 | -394 | -39.4% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0238 | PRJ-012 | Cloud Migration | Install onboarding process | IT | Tarek Abdelrahman | Low | Delayed | 1000 | 734 | 2024-02-05 | 2024-02-29 | 2024-02-29 | 24 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | IT | 180 | -266 | -26.6% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0145 | PRJ-008 | Office Relocation | Develop budget report | Finance | Farida Hosny | Medium | Delayed | 8000 | 8335 | 2024-05-26 | 2024-06-03 | 2024-06-04 | 8 | 1 | Pharos Holdings | Nourhan Tarek | 300000 | HR | 150 | 335 | 4.188% | N/A | Medium (8-20 days) | Nourhan Tarek | Delayed by 1 days
TSK-0171 | PRJ-009 | Supply Chain Optimization | Review warehouse layout | Operations | Fady Hosny | Low | Not Started | 6000 | 0 | 2024-02-14 | 2024-03-12 |  | 27 | 0 | Suez Trading Co. | Laila Samir | 100000 | HR | 300 | -6000 | -100% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0059 | PRJ-003 | Mobile App Launch | Test hardware setup | Procurement | Mostafa El-Sayed | Low | Completed | 1000 | 1106 |  |  |  |  | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Procurement | 200 | 106 | 10.6% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0131 | PRJ-007 | Network Security Overhaul | Document customer feedback survey | Operations | Salma Fouad | Medium | Ongoing | 8000 | 5450 |  |  |  |  | 0 | Internal | Laila Samir | 120000 | Quality Assurance | 200 | -2550 | -31.87% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0236 | PRJ-012 | Cloud Migration | Deploy backup procedure | HR | Khaled Naguib | Not Set | In Progress | 8000 | 4463 | 2024-05-19 | 2024-06-14 |  | 26 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Finance | 250 | -3537 | -44.21% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0186 | PRJ-009 | Supply Chain Optimization | Migrate onboarding process | HR | Reem Gaber | High | In Progress | 3000 | 742 |  |  |  |  | 0 | Suez Trading Co. | Laila Samir | 100000 | Operations | 180 | -2258 | -75.27% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0113 | PRJ-006 | CRM Migration | Test onboarding process | Quality | Dina Fouad | High | Delayed | 6000 | 7892 | 2024-07-01 | 2024-07-20 | 2024-07-31 | 19 | 11 | BlueWave Telecom | Mona Farid | 120000 | Marketing | 300 | 1892 | 31.53% | N/A | Medium (8-20 days) | Mona Farid | Delayed by 11 days
TSK-0074 | PRJ-004 | Warehouse Automation | Deploy database schema | Finance | Ziad Abdelrahman | Medium | In Progress | 2000 | 1080 | 2024-06-23 | 2024-07-01 |  | 8 | 0 | Cairo Financial Services | Laila Samir | 75000 | Finance | 220 | -920 | -46% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0072 | PRJ-004 | Warehouse Automation | Configure network infrastructure | Procurement | Fady Hosny | Low | In Progress | 3000 | 1233 | 2024-09-03 | 2024-09-25 |  | 22 | 0 | Cairo Financial Services | Laila Samir | 75000 | HR | 300 | -1767 | -58.9% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0139 | PRJ-007 | Network Security Overhaul | Migrate supplier list | HR | Khaled Younes | High | In Progress | 6000 | 1369 | 2024-09-09 | 2024-09-29 |  | 20 | 0 | Internal | Laila Samir | 120000 | Finance | 280 | -4631 | -77.18% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0071 | PRJ-004 | Warehouse Automation | Develop warehouse layout | Finance | Khaled Younes | High | Delayed | 1500 | 1832 |  |  |  |  | 0 | Cairo Financial Services | Laila Samir | 75000 | Finance | 280 | 332 | 22.13% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0273 | PRJ-014 | Retail Store Opening | Test database schema | Marketing | Farida Shawky | High | Ongoing | 2500 | 895 | 2024-02-16 | 2024-03-07 |  | 20 | 0 | Orbit Media | Ahmed Nabil | 300000 | Procurement | 250 | -1605 | -64.2% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0279 | PRJ-014 | Retail Store Opening | Design inventory system | HR | Farida Younes | Medium | Completed | 6000 | 5085 | 2024-05-14 | 2024-06-07 | 2024-06-07 | 24 | 0 | Orbit Media | Ahmed Nabil | 300000 | Operations | 180 | -915 | -15.25% | On Time | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0089 | PRJ-005 | Customer Portal Upgrade | Optimize security policy | Marketing | Sherif Hosny | Medium | In Progress | 6000 | 2042 | 2024-03-21 | 2024-04-17 |  | 27 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | Operations | 200 | -3958 | -65.97% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0173 | PRJ-009 | Supply Chain Optimization | Plan customer feedback survey | Quality | Tarek Shawky | High | In Progress | 4000 | 2867 | 2024-05-31 | 2024-06-25 |  | 25 | 0 | Suez Trading Co. | Laila Samir | 100000 | Procurement | 150 | -1133 | -28.32% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0283 | PRJ-014 | Retail Store Opening | Procure quality checklist | IT | Dina Mahmoud | High | Completed | 1000 | 1328 | 2024-02-14 | 2024-03-07 | 2024-03-08 | 22 | 1 | Orbit Media | Ahmed Nabil | 300000 | Quality Assurance | 250 | 328 | 32.8% | Late | Long (>20 days) | Ahmed Nabil | Delayed by 1 days
TSK-0003 | PRJ-001 | Website Redesign | Deploy warehouse layout | Procurement | Reem Gaber | Medium | In Progress | 3000 | 1804 | 2024-10-21 | 2024-10-31 |  | 10 | 0 | Nile Corp | Mona Farid | 75000 | Operations | 180 | -1196 | -39.87% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0154 | PRJ-008 | Office Relocation | Analyze marketing collateral | Operations | Yasmin Zaki | Low | Completed | 1500 | 1055 | 2024-05-17 | 2024-05-31 | 2024-05-28 | 14 | -3 | Pharos Holdings | Nourhan Tarek | 300000 | Operations | 220 | -445 | -29.67% | On Time | Medium (8-20 days) | Nourhan Tarek | Early by 3 days
TSK-0162 | PRJ-008 | Office Relocation | Document dashboard | HR | Yasmin El-Sayed | Medium | Delayed | 2500 | 2644 | 2024-02-28 | 2024-03-05 | 2024-03-10 | 6 | 5 | Pharos Holdings | Nourhan Tarek | 300000 | HR | 180 | 144 | 5.76% | N/A | Short (<=7 days) | Nourhan Tarek | Delayed by 5 days
TSK-0242 | PRJ-012 | Cloud Migration | Procure vendor contract | Marketing | Mariam Kamal | High | In Progress | 3000 | 1248 | 2024-02-03 | 2024-03-04 |  | 30 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 180 | -1752 | -58.4% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0039 | PRJ-002 | ERP System Rollout | Deploy warehouse layout | IT | Yasmin Younes | High | Delayed | 10000 | 11406 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | IT | 220 | 1406 | 14.06% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0002 | PRJ-001 | Website Redesign | Document warehouse layout | Procurement | Khaled Naguib | Medium | In Progress | 2500 | 837 | 2024-10-05 | 2024-10-11 |  | 6 | 0 | Nile Corp | Mona Farid | 75000 | Finance | 250 | -1663 | -66.52% | N/A | Short (<=7 days) | Mona Farid | On schedule
TSK-0264 | PRJ-013 | Brand Refresh Campaign | Plan employee handbook | HR | Hassan Fouad | Medium | Done | 2500 | 2311 | 2024-04-12 | 2024-04-24 | 2024-04-26 | 12 | 2 | Internal | Nourhan Tarek | 200000 | IT | 280 | -189 | -7.56% | N/A | Medium (8-20 days) | Nourhan Tarek | Delayed by 2 days
TSK-0035 | PRJ-002 | ERP System Rollout | Audit warehouse layout | Procurement | Ziad Abdelrahman | Low | Completed | 1500 | 1359 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Finance | 220 | -141 | -9.4% | On Time | Short (<=7 days) | Youssef Adel | On schedule
TSK-0247 | PRJ-012 | Cloud Migration | Document employee handbook | IT | Farida Zaki | Medium | Completed | 4000 | 0 | 2024-02-12 | 2024-03-10 | 2024-03-10 | 27 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Operations | 200 | -4000 | -100% | On Time | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0226 | PRJ-011 | HR System Implementation | Design inventory system | Operations | Dina Zaki | Low | Completed | 1000 | 1032 |  |  |  |  | 0 | Giza Health Systems | Ahmed Nabil | 200000 | IT | 220 | 32 | 3.2% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0265 | PRJ-013 | Brand Refresh Campaign | Install backup procedure | Operations | Dina Zaki | High | Delayed | 1500 | 1834 | 2024-08-16 | 2024-09-14 | 2024-09-24 | 29 | 10 | Internal | Nourhan Tarek | 200000 | IT | 220 | 334 | 22.27% | N/A | Long (>20 days) | Nourhan Tarek | Delayed by 10 days
TSK-0102 | PRJ-005 | Customer Portal Upgrade | Deploy dashboard |  | Yasmin Younes | Not Set | Not Started | 10000 | 0 | 2024-04-10 | 2024-04-25 |  | 15 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 220 | -10000 | -100% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0115 | PRJ-006 | CRM Migration | Train users on customer feedback survey | Finance | Yasmin El-Sayed | Low | Ongoing | 3000 | 732 | 2024-05-27 | 2024-06-16 |  | 20 | 0 | BlueWave Telecom | Mona Farid | 120000 | HR | 180 | -2268 | -75.6% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0116 | PRJ-006 | CRM Migration | Develop user interface | IT | Yasmin El-Sayed | Low | In Progress | 10000 | 5055 | 2024-04-01 | 2024-04-10 |  | 9 | 0 | BlueWave Telecom | Mona Farid | 120000 | HR | 180 | -4945 | -49.45% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0200 | PRJ-010 | Product Line Expansion | Review user interface | IT | Salma Fouad | High | Completed | 0 | 1529 | 2024-05-17 | 2024-06-09 | 2024-06-09 | 23 | 0 | Internal | Sara Hassan | 150000 | Quality Assurance | 200 | 1529 | 0% | On Time | Long (>20 days) | Sara Hassan | On schedule
TSK-0097 | PRJ-005 | Customer Portal Upgrade | Audit security policy | Procurement | Noor Naguib | Low | Completed | 1500 | 1802 | 2024-02-24 | 2024-03-23 | 2024-03-21 | 28 | -2 | Horizon Manufacturing | Ahmed Nabil | 50000 | Marketing | 280 | 302 | 20.13% | On Time | Long (>20 days) | Ahmed Nabil | Early by 2 days
TSK-0301 | PRJ-015 | Data Center Upgrade | Audit marketing collateral | Operations | Khaled Naguib | High | Completed | 8000 | 8590 | 2024-08-11 | 2024-08-18 | 2024-08-20 | 7 | 2 | Internal | Nourhan Tarek | 75000 | Finance | 250 | 590 | 7.375% | Late | Short (<=7 days) | Nourhan Tarek | Delayed by 2 days
TSK-0140 | PRJ-007 | Network Security Overhaul | Deploy onboarding process | Operations | Farida Hosny | Medium | Completed | 5000 | 6887 | 2024-09-18 | 2024-09-22 | 2024-09-23 | 4 | 1 | Internal | Laila Samir | 120000 | HR | 150 | 1887 | 37.74% | Late | Short (<=7 days) | Laila Samir | Delayed by 1 days
TSK-0241 | PRJ-012 | Cloud Migration | Test vendor contract | Procurement | Dina Zaki | High | In Progress | 10000 | 6014 | 2024-02-21 | 2024-03-21 |  | 29 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | IT | 220 | -3986 | -39.86% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0243 | PRJ-012 | Cloud Migration | Review onboarding process | IT | Khaled Naguib | Medium | Delayed | 0 | 1441 |  |  |  |  | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Finance | 250 | 1441 | 0% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0111 | PRJ-006 | CRM Migration | Deploy quality checklist | Marketing | Khaled Younes | Medium | Completed | 4000 | 4856 | 2024-04-01 | 2024-04-14 | 2024-04-16 | 13 | 2 | BlueWave Telecom | Mona Farid | 120000 | Finance | 280 | 856 | 21.4% | Late | Medium (8-20 days) | Mona Farid | Delayed by 2 days
TSK-0106 | PRJ-005 | Customer Portal Upgrade | Approve API integration | Marketing | Hassan Fouad | Medium | Ongoing | 10000 | 7305 | 2024-05-29 | 2024-06-05 |  | 7 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 280 | -2695 | -26.95% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0280 | PRJ-014 | Retail Store Opening | Design hardware setup | Operations | Ziad Abdelrahman | Low | Completed | 2000 | 2123 | 2024-01-26 | 2024-02-03 | 2024-02-02 | 8 | -1 | Orbit Media | Ahmed Nabil | 300000 | Finance | 220 | 123 | 6.15% | On Time | Medium (8-20 days) | Ahmed Nabil | Early by 1 days
TSK-0084 | PRJ-004 | Warehouse Automation | Install dashboard | IT | Yasmin Younes | Low | Not Started | 2000 | 0 |  |  |  |  | 0 | Cairo Financial Services | Laila Samir | 75000 | IT | 220 | -2000 | -100% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0193 | PRJ-010 | Product Line Expansion | Design supplier list | Procurement | Sherif Hosny | Low | In Progress | 8000 | 5250 |  |  |  |  | 0 | Internal | Sara Hassan | 150000 | Operations | 200 | -2750 | -34.38% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0310 | PRJ-015 | Data Center Upgrade | Design supplier list | IT | Dina Fouad | Medium | Completed | 6000 | 8177 | 2024-08-04 | 2024-08-24 | 2024-08-21 | 20 | -3 | Internal | Nourhan Tarek | 75000 | Marketing | 300 | 2177 | 36.28% | On Time | Medium (8-20 days) | Nourhan Tarek | Early by 3 days
TSK-0091 | PRJ-005 | Customer Portal Upgrade | Analyze database schema | Quality | Sherif Hosny | Medium | In Progress | 5000 | 1275 | 2024-05-19 | 2024-05-26 |  | 7 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | Operations | 200 | -3725 | -74.5% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0114 | PRJ-006 | CRM Migration | Deploy marketing collateral | Operations | Tarek Abdelrahman | Medium | In Progress | 8000 | 1639 | 2024-06-24 | 2024-07-06 |  | 12 | 0 | BlueWave Telecom | Mona Farid | 120000 | IT | 180 | -6361 | -79.51% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0217 | PRJ-011 | HR System Implementation | Deploy vendor contract | Marketing | Sherif Ibrahim | Low | Delayed | 5000 | 6660 | 2024-06-25 | 2024-07-07 | 2024-07-06 | 12 | -1 | Giza Health Systems | Ahmed Nabil | 200000 | Procurement | 180 | 1660 | 33.2% | N/A | Medium (8-20 days) | Ahmed Nabil | Early by 1 days
TSK-0041 | PRJ-002 | ERP System Rollout | Plan database schema | Procurement | Farida Hosny | Low | Delayed | 2000 | 1736 | 2024-09-13 | 2024-10-07 | 2024-10-06 | 24 | -1 | Delta Retail Group | Youssef Adel | 150000 | HR | 150 | -264 | -13.2% | N/A | Long (>20 days) | Youssef Adel | Early by 1 days
TSK-0087 | PRJ-004 | Warehouse Automation | Optimize security policy | Quality | Reem Gaber | High | Done | 4000 | 3665 | 2024-10-30 | 2024-11-13 | 2024-11-10 | 14 | -3 | Cairo Financial Services | Laila Samir | 75000 | Operations | 180 | -335 | -8.375% | N/A | Medium (8-20 days) | Laila Samir | Early by 3 days
TSK-0130 | PRJ-007 | Network Security Overhaul | Review hardware setup | Procurement | Sherif Ibrahim | Low | Completed | 5000 | 0 | 2024-09-19 | 2024-10-01 | 2024-09-29 | 12 | -2 | Internal | Laila Samir | 120000 | Procurement | 180 | -5000 | -100% | On Time | Medium (8-20 days) | Laila Samir | Early by 2 days
TSK-0103 | PRJ-005 | Customer Portal Upgrade | Optimize server configuration | Quality | Hana Zaki | Medium | Done | 2500 | 3431 |  |  |  |  | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 150 | 931 | 37.24% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0302 | PRJ-015 | Data Center Upgrade | Analyze quality checklist | Marketing | Khaled Naguib | High | Completed | 1500 | 1522 | 2024-08-05 | 2024-09-03 | 2024-09-05 | 29 | 2 | Internal | Nourhan Tarek | 75000 | Finance | 250 | 22 | 1.467% | Late | Long (>20 days) | Nourhan Tarek | Delayed by 2 days
TSK-0308 | PRJ-015 | Data Center Upgrade | Plan warehouse layout | Procurement | Sherif Ibrahim | Medium | Delayed | 6000 | 4767 | 2024-08-22 | 2024-09-02 | 2024-09-16 | 11 | 14 | Internal | Nourhan Tarek | 75000 | Procurement | 180 | -1233 | -20.55% | N/A | Medium (8-20 days) | Nourhan Tarek | Delayed by 14 days
TSK-0043 | PRJ-003 | Mobile App Launch | Install hardware setup | Operations | Noor Naguib | High | Completed | 10000 | 13448 | 2024-05-15 | 2024-06-06 | 2024-06-08 | 22 | 2 | Alexandria Logistics | Ahmed Nabil | 100000 | Marketing | 280 | 3448 | 34.48% | Late | Long (>20 days) | Ahmed Nabil | Delayed by 2 days
TSK-0027 | PRJ-002 | ERP System Rollout | Design budget report |  | Ziad Abdelrahman | Low | In Progress | 10000 | 5205 | 2024-11-04 | 2024-11-11 |  | 7 | 0 | Delta Retail Group | Youssef Adel | 150000 | Finance | 220 | -4795 | -47.95% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0110 | PRJ-006 | CRM Migration | Audit dashboard | HR | Aya Ibrahim | Medium | Completed | 6000 | 5228 | 2024-05-09 | 2024-06-01 | 2024-05-31 | 23 | -1 | BlueWave Telecom | Mona Farid | 120000 | Quality Assurance | 250 | -772 | -12.87% | On Time | Long (>20 days) | Mona Farid | Early by 1 days
TSK-0118 | PRJ-006 | CRM Migration | Optimize marketing collateral | Procurement | Mostafa El-Sayed | Medium | In Progress | 10000 | 3846 | 2024-03-24 | 2024-04-09 |  | 16 | 0 | BlueWave Telecom | Mona Farid | 120000 | Procurement | 200 | -6154 | -61.54% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0092 | PRJ-005 | Customer Portal Upgrade | Deploy network infrastructure | Finance | Farida Shawky | Medium | In Progress | 1500 | 1055 | 2024-01-16 | 2024-01-29 |  | 13 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | Procurement | 250 | -445 | -29.67% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0148 | PRJ-008 | Office Relocation | Audit budget report | HR | Sherif Ibrahim | Medium | Completed | 10000 | 8702 |  |  |  |  | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Procurement | 180 | -1298 | -12.98% | On Time | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0202 | PRJ-010 | Product Line Expansion | Document employee handbook | HR | Rania Gaber | Medium | Completed | 3000 | 2904 |  |  |  |  | 0 | Internal | Sara Hassan | 150000 | Marketing | 220 | -96 | -3.2% | On Time | Short (<=7 days) | Sara Hassan | On schedule
TSK-0230 | PRJ-011 | HR System Implementation | Audit training material | Marketing | Mariam Kamal | High | Done | 6000 | 8007 | 2024-04-21 | 2024-05-15 | 2024-05-16 | 24 | 1 | Giza Health Systems | Ahmed Nabil | 200000 | Procurement | 180 | 2007 | 33.45% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 1 days
TSK-0282 | PRJ-014 | Retail Store Opening | Review training material | IT | Salma Fouad | High | In Progress | 8000 | 0 |  |  |  |  | 0 | Orbit Media | Ahmed Nabil | 300000 | Quality Assurance | 200 | -8000 | -100% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0170 | PRJ-009 | Supply Chain Optimization | Plan budget report | Operations | Noor Naguib | Low | Behind Schedule | 5000 | 5985 | 2024-04-15 | 2024-05-09 | 2024-05-21 | 24 | 12 | Suez Trading Co. | Laila Samir | 100000 | Marketing | 280 | 985 | 19.7% | N/A | Long (>20 days) | Laila Samir | Delayed by 12 days
TSK-0309 | PRJ-015 | Data Center Upgrade | Analyze supplier list | Procurement | Noor Naguib | Medium | Ongoing | 2500 | 1707 | 2024-08-07 | 2024-08-27 |  | 20 | 0 | Internal | Nourhan Tarek | 75000 | Marketing | 280 | -793 | -31.72% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0234 | PRJ-012 | Cloud Migration | Approve supplier list | Finance | Farida Shawky | Low | Completed | 2000 | 2260 | 2024-05-28 | 2024-06-25 | 2024-06-22 | 28 | -3 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 250 | 260 | 13% | On Time | Long (>20 days) | Ahmed Nabil | Early by 3 days
TSK-0161 | PRJ-008 | Office Relocation | Document quality checklist | HR | Hassan Fouad | Low | Completed | 10000 | 11467 | 2024-05-28 | 2024-06-22 | 2024-06-23 | 25 | 1 | Pharos Holdings | Nourhan Tarek | 300000 | IT | 280 | 1467 | 14.67% | Late | Long (>20 days) | Nourhan Tarek | Delayed by 1 days
TSK-0146 | PRJ-008 | Office Relocation | Optimize API integration | Quality | Yasmin Younes | High | In Progress | 8000 | 3789 | 2024-02-28 | 2024-03-08 |  | 9 | 0 | Pharos Holdings | Nourhan Tarek | 300000 | IT | 220 | -4211 | -52.64% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0064 | PRJ-003 | Mobile App Launch | Analyze user interface | HR | Tarek Abdelrahman | High | Delayed | 2500 | 3247 | 2024-04-22 | 2024-05-09 | 2024-05-20 | 17 | 11 | Alexandria Logistics | Ahmed Nabil | 100000 | IT | 180 | 747 | 29.88% | N/A | Medium (8-20 days) | Ahmed Nabil | Delayed by 11 days
TSK-0221 | PRJ-011 | HR System Implementation | Design backup procedure | HR | Farida Zaki | Low | Not Started | 6000 | 0 | 2024-03-08 | 2024-04-03 |  | 26 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Operations | 200 | -6000 | -100% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0219 | PRJ-011 | HR System Implementation | Procure vendor contract | IT | Hana Zaki | Low | In Progress | 6000 | 4502 | 2024-05-05 | 2024-05-24 |  | 19 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | IT | 150 | -1498 | -24.97% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0228 | PRJ-011 | HR System Implementation | Train users on marketing collateral | Procurement | Farida Zaki | Low | Done | 6000 | 4468 | 2024-05-11 | 2024-06-04 | 2024-06-01 | 24 | -3 | Giza Health Systems | Ahmed Nabil | 200000 | Operations | 200 | -1532 | -25.53% | N/A | Long (>20 days) | Ahmed Nabil | Early by 3 days
TSK-0255 | PRJ-013 | Brand Refresh Campaign | Procure employee handbook | Procurement | Farida Hosny | Low | Delayed | 1500 | 1849 | 2024-08-07 | 2024-08-27 | 2024-09-03 | 20 | 7 | Internal | Nourhan Tarek | 200000 | HR | 150 | 349 | 23.27% | N/A | Medium (8-20 days) | Nourhan Tarek | Delayed by 7 days
TSK-0293 | PRJ-014 | Retail Store Opening | Optimize vendor contract | Finance | Fady Hosny | Low | Completed | 6000 | 7063 | 2024-03-14 | 2024-04-10 | 2024-04-09 | 27 | -1 | Orbit Media | Ahmed Nabil | 300000 | HR | 300 | 1063 | 17.72% | On Time | Long (>20 days) | Ahmed Nabil | Early by 1 days
TSK-0060 | PRJ-003 | Mobile App Launch | Install budget report | Operations | Khaled Naguib | Low | Completed | 3000 | 3668 | 2024-04-09 | 2024-04-20 | 2024-04-20 | 11 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Finance | 250 | 668 | 22.27% | On Time | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0227 | PRJ-011 | HR System Implementation | Approve warehouse layout | Finance | Unassigned | Medium | In Progress | 6000 | 2288 | 2024-04-29 | 2024-05-08 |  | 9 | 0 | Giza Health Systems | Ahmed Nabil | 200000 |  |  | -3712 | -61.87% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0133 | PRJ-007 | Network Security Overhaul | Install hardware setup | IT | Fady Hosny | High | Completed | 8000 | 7926 | 2024-06-06 | 2024-06-23 | 2024-06-21 | 17 | -2 | Internal | Laila Samir | 120000 | HR | 300 | -74 | -0.925% | On Time | Medium (8-20 days) | Laila Samir | Early by 2 days
TSK-0056 | PRJ-003 | Mobile App Launch | Plan budget report | HR | Mariam Kamal | Medium | In Progress | 6000 | 4444 | 2024-02-29 | 2024-03-28 |  | 28 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Procurement | 180 | -1556 | -25.93% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0020 | PRJ-002 | ERP System Rollout | Test hardware setup | Operations | Aya Ibrahim | Low | Done | 2500 | 2645 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Quality Assurance | 250 | 145 | 5.8% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0078 | PRJ-004 | Warehouse Automation | Procure warehouse layout | Procurement | Khaled Naguib | High | Completed | 6000 | 8069 | 2024-07-02 | 2024-07-18 | 2024-07-15 | 16 | -3 | Cairo Financial Services | Laila Samir | 75000 | Finance | 250 | 2069 | 34.48% | On Time | Medium (8-20 days) | Laila Samir | Early by 3 days
TSK-0209 | PRJ-011 | HR System Implementation | Document warehouse layout | Procurement | Tarek Shawky | Low | In Progress | 10000 | 2194 | 2024-07-20 | 2024-08-04 |  | 15 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Procurement | 150 | -7806 | -78.06% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0267 | PRJ-013 | Brand Refresh Campaign | Audit dashboard | IT | Tarek Shawky | Not Set | Not Started | 3000 | 0 | 2024-04-28 | 2024-05-10 |  | 12 | 0 | Internal | Nourhan Tarek | 200000 | Procurement | 150 | -3000 | -100% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0292 | PRJ-014 | Retail Store Opening | Audit backup procedure | HR | Hassan Fouad | Low | Completed | 8000 | 6196 | 2024-03-18 | 2024-03-26 | 2024-03-26 | 8 | 0 | Orbit Media | Ahmed Nabil | 300000 | IT | 280 | -1804 | -22.55% | On Time | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0136 | PRJ-007 | Network Security Overhaul | Train users on security policy | Operations | Khaled Younes | Medium | Completed | 2500 | 2183 |  |  |  |  | 0 | Internal | Laila Samir | 120000 | Finance | 280 | -317 | -12.68% | On Time | Short (<=7 days) | Laila Samir | On schedule
TSK-0289 | PRJ-014 | Retail Store Opening | Develop training material | Operations | Yasmin Zaki | Low | Not Started | 8000 | 0 | 2024-04-23 | 2024-05-15 |  | 22 | 0 | Orbit Media | Ahmed Nabil | 300000 | Operations | 220 | -8000 | -100% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0158 | PRJ-008 | Office Relocation | Migrate hardware setup | Marketing | Farida Younes | High | Ongoing | 2500 | 1219 | 2024-05-18 | 2024-06-09 |  | 22 | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Operations | 180 | -1281 | -51.24% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0015 | PRJ-001 | Website Redesign | Approve user interface | Quality | Sherif Ibrahim | High | Delayed | 3000 | 2434 | 2024-09-25 | 2024-10-23 | 2024-10-27 | 28 | 4 | Nile Corp | Mona Farid | 75000 | Procurement | 180 | -566 | -18.87% | N/A | Long (>20 days) | Mona Farid | Delayed by 4 days
TSK-0182 | PRJ-009 | Supply Chain Optimization | Deploy vendor contract | Procurement | Hassan Fouad | Low | In Progress | 6000 | 4296 | 2024-04-16 | 2024-05-08 |  | 22 | 0 | Suez Trading Co. | Laila Samir | 100000 | IT | 280 | -1704 | -28.4% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0262 | PRJ-013 | Brand Refresh Campaign | Optimize employee handbook | Marketing | Dina Mahmoud | Low | In Progress | 3000 | 993 | 2024-06-24 | 2024-07-08 |  | 14 | 0 | Internal | Nourhan Tarek | 200000 | Quality Assurance | 250 | -2007 | -66.9% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0107 | PRJ-006 | CRM Migration | Develop vendor contract | Operations | Dina Zaki | Not Set | Completed | 10000 | 8274 | 2024-05-23 | 2024-05-30 | 2024-05-31 | 7 | 1 | BlueWave Telecom | Mona Farid | 120000 | IT | 220 | -1726 | -17.26% | Late | Short (<=7 days) | Mona Farid | Delayed by 1 days
TSK-0313 | PRJ-015 | Data Center Upgrade | Plan vendor contract | Marketing | Farida Hosny | Medium | Ongoing | 2000 | 460 | 2024-06-27 | 2024-06-30 |  | 3 | 0 | Internal | Nourhan Tarek | 75000 | HR | 150 | -1540 | -77% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0143 | PRJ-007 | Network Security Overhaul | Analyze backup procedure | Finance | Khaled Naguib | Medium | Ongoing | 6000 | 3942 |  |  |  |  | 0 | Internal | Laila Samir | 120000 | Finance | 250 | -2058 | -34.3% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0093 | PRJ-005 | Customer Portal Upgrade | Procure vendor contract | Marketing | Dina Zaki | Medium | Completed | 3000 | 2553 | 2024-01-10 | 2024-01-15 | 2024-01-12 | 5 | -3 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 220 | -447 | -14.9% | On Time | Short (<=7 days) | Ahmed Nabil | Early by 3 days
TSK-0016 | PRJ-001 | Website Redesign | Analyze server configuration | Quality | Hassan Fouad | High | In Progress | 4000 | 1469 | 2024-07-31 | 2024-08-15 |  | 15 | 0 | Nile Corp | Mona Farid | 75000 | IT | 280 | -2531 | -63.28% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0164 | PRJ-008 | Office Relocation | Design backup procedure | Operations | Sherif Ibrahim | High | Completed | 3000 | 2194 | 2024-06-20 | 2024-07-03 | 2024-06-30 | 13 | -3 | Pharos Holdings | Nourhan Tarek | 300000 | Procurement | 180 | -806 | -26.87% | On Time | Medium (8-20 days) | Nourhan Tarek | Early by 3 days
TSK-0029 | PRJ-002 | ERP System Rollout | Design customer feedback survey | IT | Sherif Hosny | High | Not Started | 1000 | 0 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Operations | 200 | -1000 | -100% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0287 | PRJ-014 | Retail Store Opening | Document dashboard | Finance | Mariam Kamal | Low | In Progress | 2000 | 1426 | 2024-04-22 | 2024-05-18 |  | 26 | 0 | Orbit Media | Ahmed Nabil | 300000 | Procurement | 180 | -574 | -28.7% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0220 | PRJ-011 | HR System Implementation | Optimize user interface | HR | Dina Fouad | High | Behind Schedule | 3000 | 2904 | 2024-07-11 | 2024-07-25 | 2024-08-04 | 14 | 10 | Giza Health Systems | Ahmed Nabil | 200000 | Marketing | 300 | -96 | -3.2% | N/A | Medium (8-20 days) | Ahmed Nabil | Delayed by 10 days
TSK-0168 | PRJ-009 | Supply Chain Optimization | Approve supplier list | Finance | Dina Zaki | High | In Progress | 5000 | 2255 | 2024-02-07 | 2024-02-26 |  | 19 | 0 | Suez Trading Co. | Laila Samir | 100000 | IT | 220 | -2745 | -54.9% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0054 | PRJ-003 | Mobile App Launch | Design user interface | IT | Sherif Ibrahim | High | Completed | 1500 | 1516 | 2024-06-17 | 2024-06-23 | 2024-06-25 | 6 | 2 | Alexandria Logistics | Ahmed Nabil | 100000 | Procurement | 180 | 16 | 1.067% | Late | Short (<=7 days) | Ahmed Nabil | Delayed by 2 days
TSK-0004 | PRJ-001 | Website Redesign | Review user interface | Marketing | Mostafa El-Sayed | Low | In Progress | 5000 | 2401 | 2024-09-10 | 2024-09-26 |  | 16 | 0 | Nile Corp | Mona Farid | 75000 | Procurement | 200 | -2599 | -51.98% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0019 | PRJ-001 | Website Redesign | Audit onboarding process | Finance | Farida Younes | Low | In Progress | 5000 | 3032 | 2024-07-31 | 2024-08-16 |  | 16 | 0 | Nile Corp | Mona Farid | 75000 | Operations | 180 | -1968 | -39.36% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0290 | PRJ-014 | Retail Store Opening | Plan budget report | Operations | Farida Shawky | Low | In Progress | 1000 | 416 | 2024-02-24 | 2024-03-19 |  | 24 | 0 | Orbit Media | Ahmed Nabil | 300000 | Procurement | 250 | -584 | -58.4% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0156 | PRJ-008 | Office Relocation | Test training material | IT | Dina Fouad | Low | Delayed | 3000 | 2732 |  |  |  |  | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Marketing | 300 | -268 | -8.933% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0057 | PRJ-003 | Mobile App Launch | Document onboarding process | HR | Dina Fouad | Low | Completed | 2500 | 3499 | 2024-06-22 | 2024-07-22 | 2024-07-21 | 30 | -1 | Alexandria Logistics | Ahmed Nabil | 100000 | Marketing | 300 | 999 | 39.96% | On Time | Long (>20 days) | Ahmed Nabil | Early by 1 days
TSK-0094 | PRJ-005 | Customer Portal Upgrade | Document network infrastructure | IT | Hana Zaki | Medium | Ongoing | 6000 | 3348 | 2024-02-06 | 2024-03-06 |  | 29 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | IT | 150 | -2652 | -44.2% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0013 | PRJ-001 | Website Redesign | Develop quality checklist | Finance | Sherif Ibrahim | Low | Done | 1500 | 2042 |  |  |  |  | 0 | Nile Corp | Mona Farid | 75000 | Procurement | 180 | 542 | 36.13% | N/A | Short (<=7 days) | Mona Farid | On schedule
TSK-0066 | PRJ-003 | Mobile App Launch | Review database schema | HR | Aya Ibrahim | Medium | Completed | 2000 | 2156 |  |  |  |  | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Quality Assurance | 250 | 156 | 7.8% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0269 | PRJ-013 | Brand Refresh Campaign | Deploy training material | IT | Farida Shawky | Low | Completed | 4000 | 3393 | 2024-06-18 | 2024-06-27 | 2024-06-29 | 9 | 2 | Internal | Nourhan Tarek | 200000 | Procurement | 250 | -607 | -15.17% | Late | Medium (8-20 days) | Nourhan Tarek | Delayed by 2 days
TSK-0180 | PRJ-009 | Supply Chain Optimization | Review supplier list | IT | Sherif Ibrahim | High | In Progress | 6000 | 1233 | 2024-05-13 | 2024-06-06 |  | 24 | 0 | Suez Trading Co. | Laila Samir | 100000 | Procurement | 180 | -4767 | -79.45% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0160 | PRJ-008 | Office Relocation | Approve budget report | Quality | Dina Zaki | Medium | Completed | 0 | 2192 | 2024-04-01 | 2024-04-24 | 2024-04-23 | 23 | -1 | Pharos Holdings | Nourhan Tarek | 300000 | IT | 220 | 2192 | 0% | On Time | Long (>20 days) | Nourhan Tarek | Early by 1 days
TSK-0254 | PRJ-013 | Brand Refresh Campaign | Configure security policy | Marketing | Sherif Ibrahim | Low | Pending | 4000 | 0 | 2024-08-19 | 2024-09-18 |  | 30 | 0 | Internal | Nourhan Tarek | 200000 | Procurement | 180 | -4000 | -100% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0126 | PRJ-007 | Network Security Overhaul | Develop database schema | Procurement | Farida Younes | High | In Progress | 5000 | 3364 | 2024-07-07 | 2024-07-11 |  | 4 | 0 | Internal | Laila Samir | 120000 | Operations | 180 | -1636 | -32.72% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0239 | PRJ-012 | Cloud Migration | Procure vendor contract | Procurement | Tarek Shawky | Medium | In Progress | 8000 | 2896 |  |  |  |  | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 150 | -5104 | -63.8% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0100 | PRJ-005 | Customer Portal Upgrade | Plan dashboard | Quality | Sherif Ibrahim | High | Completed | 3000 | 3036 | 2024-04-01 | 2024-04-25 | 2024-04-24 | 24 | -1 | Horizon Manufacturing | Ahmed Nabil | 50000 | Procurement | 180 | 36 | 1.2% | On Time | Long (>20 days) | Ahmed Nabil | Early by 1 days
TSK-0215 | PRJ-011 | HR System Implementation | Analyze training material | Marketing | Khaled Younes | Medium | In Progress | 8000 | 3460 | 2024-05-02 | 2024-05-07 |  | 5 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | Finance | 280 | -4540 | -56.75% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0147 | PRJ-008 | Office Relocation | Review vendor contract | Marketing | Aya Ibrahim | Low | Not Started | 5000 | 0 |  |  |  |  | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Quality Assurance | 250 | -5000 | -100% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0232 | PRJ-012 | Cloud Migration | Audit supplier list | Marketing | Ziad Abdelrahman | Low | Done | 1500 | 1961 | 2024-05-23 | 2024-06-01 | 2024-06-02 | 9 | 1 | Red Sea Tourism | Ahmed Nabil | 250000 | Finance | 220 | 461 | 30.73% | N/A | Medium (8-20 days) | Ahmed Nabil | Delayed by 1 days
TSK-0026 | PRJ-002 | ERP System Rollout | Document API integration | Quality | Salma Fouad | Medium | Behind Schedule | 5000 | 6487 | 2024-07-09 | 2024-07-23 | 2024-07-29 | 14 | 6 | Delta Retail Group | Youssef Adel | 150000 | Quality Assurance | 200 | 1487 | 29.74% | N/A | Medium (8-20 days) | Youssef Adel | Delayed by 6 days
TSK-0050 | PRJ-003 | Mobile App Launch | Deploy dashboard | Marketing | Mariam Kamal | Medium | Behind Schedule | 10000 | 11059 | 2024-05-09 | 2024-06-04 | 2024-06-10 | 26 | 6 | Alexandria Logistics | Ahmed Nabil | 100000 | Procurement | 180 | 1059 | 10.59% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 6 days
TSK-0028 | PRJ-002 | ERP System Rollout | Train users on supplier list | Marketing | Dina Mahmoud | Medium | Not Started | 4000 | 0 | 2024-11-01 | 2024-11-14 |  | 13 | 0 | Delta Retail Group | Youssef Adel | 150000 | Quality Assurance | 250 | -4000 | -100% | N/A | Medium (8-20 days) | Youssef Adel | On schedule
TSK-0052 | PRJ-003 | Mobile App Launch | Deploy supplier list | Procurement | Noor Naguib | High | Completed | 1500 | 1602 | 2024-03-23 | 2024-04-22 | 2024-04-22 | 30 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Marketing | 280 | 102 | 6.8% | On Time | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0009 | PRJ-001 | Website Redesign | Audit dashboard | HR | Ziad Abdelrahman | Low | Completed | 4000 | 3468 |  |  |  |  | 0 | Nile Corp | Mona Farid | 75000 | Finance | 220 | -532 | -13.3% | On Time | Short (<=7 days) | Mona Farid | On schedule
TSK-0224 | PRJ-011 | HR System Implementation | Review database schema | Quality | Yasmin El-Sayed | High | In Progress | 4000 | 2776 | 2024-04-15 | 2024-04-26 |  | 11 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | HR | 180 | -1224 | -30.6% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0312 | PRJ-015 | Data Center Upgrade | Test training material | Operations | Rania Gaber | Low | Done | 8000 | 10129 |  |  |  |  | 0 | Internal | Nourhan Tarek | 75000 | Marketing | 220 | 2129 | 26.61% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0034 | PRJ-002 | ERP System Rollout | Design server configuration | IT | Tarek Shawky | Medium | Delayed | 4000 | 3583 | 2024-10-06 | 2024-11-03 | 2024-11-08 | 28 | 5 | Delta Retail Group | Youssef Adel | 150000 | Procurement | 150 | -417 | -10.42% | N/A | Long (>20 days) | Youssef Adel | Delayed by 5 days
TSK-0214 | PRJ-011 | HR System Implementation | Configure training material | Marketing | Tarek Abdelrahman | High | In Progress | 10000 | 4882 | 2024-03-18 | 2024-03-30 |  | 12 | 0 | Giza Health Systems | Ahmed Nabil | 200000 | IT | 180 | -5118 | -51.18% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0012 | PRJ-001 | Website Redesign | Develop database schema | Finance | Salma Fouad | Low | Completed | 1500 | 1716 | 2024-08-15 | 2024-09-14 | 2024-09-11 | 30 | -3 | Nile Corp | Mona Farid | 75000 | Quality Assurance | 200 | 216 | 14.4% | On Time | Long (>20 days) | Mona Farid | Early by 3 days
TSK-0018 | PRJ-001 | Website Redesign | Migrate vendor contract | HR | Khaled Naguib | Not Set | In Progress | 1500 | 1154 | 2024-09-13 | 2024-09-29 |  | 16 | 0 | Nile Corp | Mona Farid | 75000 | Finance | 250 | -346 | -23.07% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0169 | PRJ-009 | Supply Chain Optimization | Develop quality checklist | Procurement | Noor Naguib | Low | Delayed | 2000 | 1840 | 2024-05-06 | 2024-05-18 | 2024-05-19 | 12 | 1 | Suez Trading Co. | Laila Samir | 100000 | Marketing | 280 | -160 | -8% | N/A | Medium (8-20 days) | Laila Samir | Delayed by 1 days
TSK-0134 | PRJ-007 | Network Security Overhaul | Optimize user interface | Quality | Yasmin Younes | High | Done | 1500 | 1618 | 2024-09-08 | 2024-09-22 | 2024-09-24 | 14 | 2 | Internal | Laila Samir | 120000 | IT | 220 | 118 | 7.867% | N/A | Medium (8-20 days) | Laila Samir | Delayed by 2 days
TSK-0025 | PRJ-002 | ERP System Rollout | Develop security policy | Operations | Noor Naguib | Low | In Progress | 5000 | 1993 | 2024-07-24 | 2024-08-09 |  | 16 | 0 | Delta Retail Group | Youssef Adel | 150000 | Marketing | 280 | -3007 | -60.14% | N/A | Medium (8-20 days) | Youssef Adel | On schedule
TSK-0246 | PRJ-012 | Cloud Migration | Deploy employee handbook | Quality | Mariam Kamal | Low | Delayed | 6000 | 5652 | 2024-05-13 | 2024-06-06 | 2024-06-10 | 24 | 4 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 180 | -348 | -5.8% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 4 days
TSK-0258 | PRJ-013 | Brand Refresh Campaign | Train users on security policy | Quality | Yasmin Younes | Medium | Completed | 4000 | 5504 | 2024-07-16 | 2024-08-13 | 2024-08-15 | 28 | 2 | Internal | Nourhan Tarek | 200000 | IT | 220 | 1504 | 37.6% | Late | Long (>20 days) | Nourhan Tarek | Delayed by 2 days
TSK-0105 | PRJ-005 | Customer Portal Upgrade | Review security policy | Finance | Yasmin El-Sayed | Low | Done | 2000 | 2511 |  |  |  |  | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | HR | 180 | 511 | 25.55% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0274 | PRJ-014 | Retail Store Opening | Audit network infrastructure | Quality | Sherif Hosny | High | Completed | 2000 | 1912 | 2024-05-30 | 2024-06-19 | 2024-06-19 | 20 | 0 | Orbit Media | Ahmed Nabil | 300000 | Operations | 200 | -88 | -4.4% | On Time | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0073 | PRJ-004 | Warehouse Automation | Design customer feedback survey | IT | Salma Fouad | High | Completed | 8000 | 11057 | 2024-11-15 | 2024-11-25 | 2024-11-25 | 10 | 0 | Cairo Financial Services | Laila Samir | 75000 | Quality Assurance | 200 | 3057 | 38.21% | On Time | Medium (8-20 days) | Laila Samir | On schedule
TSK-0157 | PRJ-008 | Office Relocation | Migrate customer feedback survey | Marketing | Hana Zaki | Low | In Progress | 1500 | 422 | 2024-04-16 | 2024-05-03 |  | 17 | 0 | Pharos Holdings | Nourhan Tarek | 300000 | IT | 150 | -1078 | -71.87% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0040 | PRJ-002 | ERP System Rollout | Audit warehouse layout | Operations | Fady Hosny | Low | Completed | 6000 | 5449 | 2024-11-18 | 2024-12-03 | 2024-12-03 | 15 | 0 | Delta Retail Group | Youssef Adel | 150000 | HR | 300 | -551 | -9.183% | On Time | Medium (8-20 days) | Youssef Adel | On schedule
TSK-0099 | PRJ-005 | Customer Portal Upgrade | Test supplier list | Marketing | Yasmin El-Sayed | Medium | Delayed | 4000 | 5388 | 2024-05-15 | 2024-06-09 | 2024-06-21 | 25 | 12 | Horizon Manufacturing | Ahmed Nabil | 50000 | HR | 180 | 1388 | 34.7% | N/A | Long (>20 days) | Ahmed Nabil | Delayed by 12 days
TSK-0197 | PRJ-010 | Product Line Expansion | Plan hardware setup | Finance | Tarek Abdelrahman | High | Not Started | 3000 | 0 | 2024-06-14 | 2024-07-01 |  | 17 | 0 | Internal | Sara Hassan | 150000 | IT | 180 | -3000 | -100% | N/A | Medium (8-20 days) | Sara Hassan | On schedule
TSK-0311 | PRJ-015 | Data Center Upgrade | Approve inventory system | Quality | Farida Shawky | Medium | Completed | 2000 | 2401 | 2024-07-26 | 2024-08-10 | 2024-08-08 | 15 | -2 | Internal | Nourhan Tarek | 75000 | Procurement | 250 | 401 | 20.05% | On Time | Medium (8-20 days) | Nourhan Tarek | Early by 2 days
TSK-0175 | PRJ-009 | Supply Chain Optimization | Optimize network infrastructure | IT | Mariam Kamal | Low | Delayed | 2500 | 3083 | 2024-03-05 | 2024-03-12 | 2024-03-19 | 7 | 7 | Suez Trading Co. | Laila Samir | 100000 | Procurement | 180 | 583 | 23.32% | N/A | Short (<=7 days) | Laila Samir | Delayed by 7 days
TSK-0268 | PRJ-013 | Brand Refresh Campaign | Design employee handbook | IT | Aya Ibrahim | High | In Progress | 2000 | 758 | 2024-08-18 | 2024-08-30 |  | 12 | 0 | Internal | Nourhan Tarek | 200000 | Quality Assurance | 250 | -1242 | -62.1% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0049 | PRJ-003 | Mobile App Launch | Deploy budget report | Procurement | Reem Gaber | Not Set | Completed | 8000 | 6410 | 2024-06-26 | 2024-07-06 | 2024-07-06 | 10 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Operations | 180 | -1590 | -19.88% | On Time | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0199 | PRJ-010 | Product Line Expansion | Approve quality checklist | HR | Dina Zaki | High | Not Started | 2500 | 0 |  |  |  |  | 0 | Internal | Sara Hassan | 150000 | IT | 220 | -2500 | -100% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0033 | PRJ-002 | ERP System Rollout | Install warehouse layout | Marketing | Noor Naguib | Medium | Ongoing | 1500 | 551 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Marketing | 280 | -949 | -63.27% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0165 | PRJ-008 | Office Relocation | Plan supplier list | Operations | Farida Shawky | High | Done | 2500 | 3146 |  |  |  |  | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Procurement | 250 | 646 | 25.84% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0123 | PRJ-006 | CRM Migration | Optimize security policy | Marketing | Farida Shawky | Medium | Delayed | 4000 | 5387 | 2024-05-08 | 2024-06-02 | 2024-06-01 | 25 | -1 | BlueWave Telecom | Mona Farid | 120000 | Procurement | 250 | 1387 | 34.67% | N/A | Long (>20 days) | Mona Farid | Early by 1 days
TSK-0187 | PRJ-009 | Supply Chain Optimization | Develop hardware setup | Procurement | Tarek Abdelrahman | Low | Completed | 1500 | 2021 | 2024-03-03 | 2024-03-07 | 2024-03-05 | 4 | -2 | Suez Trading Co. | Laila Samir | 100000 | IT | 180 | 521 | 34.73% | On Time | Short (<=7 days) | Laila Samir | Early by 2 days
TSK-0010 | PRJ-001 | Website Redesign | Document quality checklist | IT | Khaled Younes | High | Done | 3000 | 2378 | 2024-10-27 | 2024-11-05 | 2024-11-06 | 9 | 1 | Nile Corp | Mona Farid | 75000 | Finance | 280 | -622 | -20.73% | N/A | Medium (8-20 days) | Mona Farid | Delayed by 1 days
TSK-0095 | PRJ-005 | Customer Portal Upgrade | Design onboarding process | Finance | Aya Ibrahim | Low | Completed | 8000 | 8647 | 2024-05-22 | 2024-06-05 | 2024-06-02 | 14 | -3 | Horizon Manufacturing | Ahmed Nabil | 50000 | Quality Assurance | 250 | 647 | 8.088% | On Time | Medium (8-20 days) | Ahmed Nabil | Early by 3 days
TSK-0195 | PRJ-010 | Product Line Expansion | Test warehouse layout | Operations | Salma Fouad | Medium | In Progress | 8000 | 2241 | 2024-08-23 | 2024-08-29 |  | 6 | 0 | Internal | Sara Hassan | 150000 | Quality Assurance | 200 | -5759 | -71.99% | N/A | Short (<=7 days) | Sara Hassan | On schedule
TSK-0260 | PRJ-013 | Brand Refresh Campaign | Migrate customer feedback survey | Finance | Yasmin Younes | Medium | Pending | 2000 | 0 |  |  |  |  | 0 | Internal | Nourhan Tarek | 200000 | IT | 220 | -2000 | -100% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0001 | PRJ-001 | Website Redesign | Configure employee handbook | IT | Tarek Shawky | High | Done | 3000 | 3208 | 2024-10-11 | 2024-10-31 | 2024-10-29 | 20 | -2 | Nile Corp | Mona Farid | 75000 | Procurement | 150 | 208 | 6.933% | N/A | Medium (8-20 days) | Mona Farid | Early by 2 days
TSK-0233 | PRJ-012 | Cloud Migration | Plan backup procedure | Operations | Dina Fouad | Medium | Ongoing | 2000 | 1335 | 2024-04-13 | 2024-05-13 |  | 30 | 0 | Red Sea Tourism | Ahmed Nabil | 250000 | Marketing | 300 | -665 | -33.25% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0188 | PRJ-010 | Product Line Expansion | Review database schema | IT | Dina Zaki | High | Completed | 3000 | 2451 | 2024-06-24 | 2024-07-13 | 2024-07-14 | 19 | 1 | Internal | Sara Hassan | 150000 | IT | 220 | -549 | -18.3% | Late | Medium (8-20 days) | Sara Hassan | Delayed by 1 days
TSK-0135 | PRJ-007 | Network Security Overhaul | Plan employee handbook | Operations | Khaled Younes | Medium | In Progress | 8000 | 2238 | 2024-08-27 | 2024-09-01 |  | 5 | 0 | Internal | Laila Samir | 120000 | Finance | 280 | -5762 | -72.02% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0152 | PRJ-008 | Office Relocation | Approve backup procedure | Procurement | Khaled Naguib | High | Not Started | 1500 | 0 | 2024-06-16 | 2024-06-26 |  | 10 | 0 | Pharos Holdings | Nourhan Tarek | 300000 | Finance | 250 | -1500 | -100% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0231 | PRJ-012 | Cloud Migration | Procure backup procedure | Finance | Mostafa El-Sayed | Low | Completed | 2500 | 2372 | 2024-04-18 | 2024-05-11 | 2024-05-08 | 23 | -3 | Red Sea Tourism | Ahmed Nabil | 250000 | Procurement | 200 | -128 | -5.12% | On Time | Long (>20 days) | Ahmed Nabil | Early by 3 days
TSK-0314 | PRJ-015 | Data Center Upgrade | Analyze dashboard | Marketing | Aya Ibrahim | High | In Progress | 5000 | 1935 | 2024-05-31 | 2024-06-13 |  | 13 | 0 | Internal | Nourhan Tarek | 75000 | Quality Assurance | 250 | -3065 | -61.3% | N/A | Medium (8-20 days) | Nourhan Tarek | On schedule
TSK-0272 | PRJ-014 | Retail Store Opening | Optimize dashboard | Marketing | Dina Zaki | High | Not Started | 4000 | 0 | 2024-03-22 | 2024-04-20 |  | 29 | 0 | Orbit Media | Ahmed Nabil | 300000 | IT | 220 | -4000 | -100% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0036 | PRJ-002 | ERP System Rollout | Migrate vendor contract | Finance | Mostafa El-Sayed | Medium | Behind Schedule | 3000 | 2584 |  |  |  |  | 0 | Delta Retail Group | Youssef Adel | 150000 | Procurement | 200 | -416 | -13.87% | N/A | Short (<=7 days) | Youssef Adel | On schedule
TSK-0083 | PRJ-004 | Warehouse Automation | Configure backup procedure | IT | Aya Ibrahim | Medium | Completed | 1000 | 1015 | 2024-11-10 | 2024-12-08 | 2024-12-10 | 28 | 2 | Cairo Financial Services | Laila Samir | 75000 | Quality Assurance | 250 | 15 | 1.5% | Late | Long (>20 days) | Laila Samir | Delayed by 2 days
TSK-0141 | PRJ-007 | Network Security Overhaul | Configure API integration | Procurement | Hassan Fouad | High | Delayed | 10000 | 11220 |  |  |  |  | 0 | Internal | Laila Samir | 120000 | IT | 280 | 1220 | 12.2% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0240 | PRJ-012 | Cloud Migration | Plan user interface | Finance | Rania Gaber | High | Completed | 2500 | 2376 | 2024-03-31 | 2024-04-29 | 2024-04-30 | 29 | 1 | Red Sea Tourism | Ahmed Nabil | 250000 | Marketing | 220 | -124 | -4.96% | Late | Long (>20 days) | Ahmed Nabil | Delayed by 1 days
TSK-0166 | PRJ-008 | Office Relocation | Plan quality checklist | Operations | Aya Ibrahim | High | Completed | 0 | 1656 | 2024-04-18 | 2024-04-29 | 2024-05-01 | 11 | 2 | Pharos Holdings | Nourhan Tarek | 300000 | Quality Assurance | 250 | 1656 | 0% | Late | Medium (8-20 days) | Nourhan Tarek | Delayed by 2 days
TSK-0179 | PRJ-009 | Supply Chain Optimization | Audit inventory system | Quality | Yasmin Younes | Medium | Not Started | 2000 | 0 | 2024-04-06 | 2024-04-30 |  | 24 | 0 | Suez Trading Co. | Laila Samir | 100000 | IT | 220 | -2000 | -100% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0096 | PRJ-005 | Customer Portal Upgrade | Deploy user interface | Marketing | Mostafa El-Sayed | Medium | In Progress | 1500 | 994 | 2024-04-06 | 2024-04-16 |  | 10 | 0 | Horizon Manufacturing | Ahmed Nabil | 50000 | Procurement | 200 | -506 | -33.73% | N/A | Medium (8-20 days) | Ahmed Nabil | On schedule
TSK-0098 | PRJ-005 | Customer Portal Upgrade | Migrate marketing collateral | IT | Dina Mahmoud | Medium | Behind Schedule | 2500 | 2251 | 2024-05-09 | 2024-05-20 | 2024-05-18 | 11 | -2 | Horizon Manufacturing | Ahmed Nabil | 50000 | Quality Assurance | 250 | -249 | -9.96% | N/A | Medium (8-20 days) | Ahmed Nabil | Early by 2 days
TSK-0251 | PRJ-013 | Brand Refresh Campaign | Configure backup procedure | Quality | Reem Gaber | High | Pending | 5000 | 0 | 2024-05-01 | 2024-05-31 |  | 30 | 0 | Internal | Nourhan Tarek | 200000 | Operations | 180 | -5000 | -100% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0278 | PRJ-014 | Retail Store Opening | Train users on security policy | Marketing | Hassan Fouad | Medium | Completed | 6000 | 4896 | 2024-01-13 | 2024-02-01 | 2024-01-30 | 19 | -2 | Orbit Media | Ahmed Nabil | 300000 | IT | 280 | -1104 | -18.4% | On Time | Medium (8-20 days) | Ahmed Nabil | Early by 2 days
TSK-0151 | PRJ-008 | Office Relocation | Migrate onboarding process | Operations | Fady Hosny | High | Not Started | 2500 | 0 | 2024-04-07 | 2024-04-28 |  | 21 | 0 | Pharos Holdings | Nourhan Tarek | 300000 | HR | 300 | -2500 | -100% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0294 | PRJ-015 | Data Center Upgrade | Audit budget report | Procurement | Farida Zaki | Medium | In Progress | 1000 | 620 |  |  |  |  | 0 | Internal | Nourhan Tarek | 75000 | Operations | 200 | -380 | -38% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0249 | PRJ-012 | Cloud Migration | Document dashboard | IT | Khaled Younes | Low | Done | 6000 | 8191 | 2024-06-02 | 2024-06-22 | 2024-06-20 | 20 | -2 | Red Sea Tourism | Ahmed Nabil | 250000 | Finance | 280 | 2191 | 36.52% | N/A | Medium (8-20 days) | Ahmed Nabil | Early by 2 days
TSK-0021 | PRJ-002 | ERP System Rollout | Test dashboard | Finance | Sherif Hosny | Low | Completed | 2000 | 1434 | 2024-09-03 | 2024-10-01 | 2024-09-29 | 28 | -2 | Delta Retail Group | Youssef Adel | 150000 | Operations | 200 | -566 | -28.3% | On Time | Long (>20 days) | Youssef Adel | Early by 2 days
TSK-0129 | PRJ-007 | Network Security Overhaul | Audit warehouse layout | IT | Farida Zaki | Medium | Delayed | 2500 | 2532 | 2024-05-24 | 2024-06-04 | 2024-06-13 | 11 | 9 | Internal | Laila Samir | 120000 | Operations | 200 | 32 | 1.28% | N/A | Medium (8-20 days) | Laila Samir | Delayed by 9 days
TSK-0069 | PRJ-004 | Warehouse Automation | Audit dashboard | IT | Tarek Shawky | High | Completed | 4000 | 3867 | 2024-11-18 | 2024-12-08 | 2024-12-10 | 20 | 2 | Cairo Financial Services | Laila Samir | 75000 | Procurement | 150 | -133 | -3.325% | Late | Medium (8-20 days) | Laila Samir | Delayed by 2 days
TSK-0184 | PRJ-009 | Supply Chain Optimization | Design quality checklist | Procurement | Tarek Shawky | High | In Progress | 2500 | 1249 | 2024-04-09 | 2024-04-15 |  | 6 | 0 | Suez Trading Co. | Laila Samir | 100000 | Procurement | 150 | -1251 | -50.04% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0194 | PRJ-010 | Product Line Expansion | Develop network infrastructure | Procurement | Rania Gaber | High | Delayed | 8000 | 11105 | 2024-06-14 | 2024-06-20 | 2024-06-23 | 6 | 3 | Internal | Sara Hassan | 150000 | Marketing | 220 | 3105 | 38.81% | N/A | Short (<=7 days) | Sara Hassan | Delayed by 3 days
TSK-0011 | PRJ-001 | Website Redesign | Deploy marketing collateral | HR | Mostafa El-Sayed | High | Done | 1500 | 1984 | 2024-07-08 | 2024-07-15 | 2024-07-14 | 7 | -1 | Nile Corp | Mona Farid | 75000 | Procurement | 200 | 484 | 32.27% | N/A | Short (<=7 days) | Mona Farid | Early by 1 days
TSK-0225 | PRJ-011 | HR System Implementation | Plan warehouse layout | Marketing | Ziad Abdelrahman | Low | Delayed | 1500 | 1349 | 2024-05-23 | 2024-05-31 | 2024-06-05 | 8 | 5 | Giza Health Systems | Ahmed Nabil | 200000 | Finance | 220 | -151 | -10.07% | N/A | Medium (8-20 days) | Ahmed Nabil | Delayed by 5 days
TSK-0178 | PRJ-009 | Supply Chain Optimization | Configure network infrastructure | Marketing | Hana Zaki | High | Delayed | 2000 | 2018 | 2024-04-28 | 2024-05-01 | 2024-05-01 | 3 | 0 | Suez Trading Co. | Laila Samir | 100000 | IT | 150 | 18 | 0.9% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0286 | PRJ-014 | Retail Store Opening | Procure employee handbook | HR | Ziad Abdelrahman | Medium | Ongoing | 3000 | 2385 |  |  |  |  | 0 | Orbit Media | Ahmed Nabil | 300000 | Finance | 220 | -615 | -20.5% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0163 | PRJ-008 | Office Relocation | Deploy quality checklist | Procurement | Hassan Fouad | Medium | Completed | 5000 | 6722 | 2024-06-28 | 2024-07-04 | 2024-07-03 | 6 | -1 | Pharos Holdings | Nourhan Tarek | 300000 | IT | 280 | 1722 | 34.44% | On Time | Short (<=7 days) | Nourhan Tarek | Early by 1 days
TSK-0120 | PRJ-006 | CRM Migration | Deploy server configuration | Operations | Dina Fouad | High | In Progress | 8000 | 5320 | 2024-04-17 | 2024-05-03 |  | 16 | 0 | BlueWave Telecom | Mona Farid | 120000 | Marketing | 300 | -2680 | -33.5% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0250 | PRJ-012 | Cloud Migration | Analyze vendor contract | HR | Khaled Younes | Low | Completed | 2500 | 1754 | 2024-02-22 | 2024-02-28 | 2024-03-01 | 6 | 2 | Red Sea Tourism | Ahmed Nabil | 250000 | Finance | 280 | -746 | -29.84% | Late | Short (<=7 days) | Ahmed Nabil | Delayed by 2 days
TSK-0065 | PRJ-003 | Mobile App Launch | Configure budget report | IT | Sherif Hosny | Low | Not Started | 4000 | 0 |  |  |  |  | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Operations | 200 | -4000 | -100% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0055 | PRJ-003 | Mobile App Launch | Approve customer feedback survey | Finance | Hassan Fouad | Low | In Progress | 2000 | 604 | 2024-07-20 | 2024-08-13 |  | 24 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | IT | 280 | -1396 | -69.8% | N/A | Long (>20 days) | Ahmed Nabil | On schedule
TSK-0275 | PRJ-014 | Retail Store Opening | Optimize quality checklist | Marketing | Fady Hosny | Low | Completed | 2000 | 1651 |  |  |  |  | 0 | Orbit Media | Ahmed Nabil | 300000 | HR | 300 | -349 | -17.45% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0079 | PRJ-004 | Warehouse Automation | Approve server configuration | Finance | Sherif Hosny | High | In Progress | 5000 | 3533 | 2024-09-22 | 2024-09-27 |  | 5 | 0 | Cairo Financial Services | Laila Samir | 75000 | Operations | 200 | -1467 | -29.34% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0183 | PRJ-009 | Supply Chain Optimization | Audit security policy | Marketing | Yasmin Zaki | Medium | Completed | 10000 | 12048 | 2024-03-05 | 2024-03-25 | 2024-03-26 | 20 | 1 | Suez Trading Co. | Laila Samir | 100000 | Operations | 220 | 2048 | 20.48% | Late | Medium (8-20 days) | Laila Samir | Delayed by 1 days
TSK-0031 | PRJ-002 | ERP System Rollout | Develop quality checklist | Finance | Tarek Shawky | High | In Progress | 3000 | 2131 | 2024-08-03 | 2024-08-28 |  | 25 | 0 | Delta Retail Group | Youssef Adel | 150000 | Procurement | 150 | -869 | -28.97% | N/A | Long (>20 days) | Youssef Adel | On schedule
TSK-0174 | PRJ-009 | Supply Chain Optimization | Review network infrastructure | Operations | Farida Zaki | Medium | Done | 3000 | 2708 | 2024-05-18 | 2024-05-26 | 2024-05-25 | 8 | -1 | Suez Trading Co. | Laila Samir | 100000 | Operations | 200 | -292 | -9.733% | N/A | Medium (8-20 days) | Laila Samir | Early by 1 days
TSK-0047 | PRJ-003 | Mobile App Launch | Audit dashboard | IT | Farida Hosny | High | Completed | 1000 | 842 |  |  |  |  | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | HR | 150 | -158 | -15.8% | On Time | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0256 | PRJ-013 | Brand Refresh Campaign | Audit marketing collateral | Quality | Aya Ibrahim | Medium | Completed | 2500 | 2217 |  |  |  |  | 0 | Internal | Nourhan Tarek | 200000 | Quality Assurance | 250 | -283 | -11.32% | On Time | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0081 | PRJ-004 | Warehouse Automation | Migrate backup procedure | Operations | Noor Naguib | High | In Progress | 10000 | 6559 | 2024-10-18 | 2024-11-14 |  | 27 | 0 | Cairo Financial Services | Laila Samir | 75000 | Marketing | 280 | -3441 | -34.41% | N/A | Long (>20 days) | Laila Samir | On schedule
TSK-0128 | PRJ-007 | Network Security Overhaul | Procure server configuration | Procurement | Unassigned | Medium | Not Started | 10000 | 0 | 2024-07-11 | 2024-07-19 |  | 8 | 0 | Internal | Laila Samir | 120000 |  |  | -10000 | -100% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0046 | PRJ-003 | Mobile App Launch | Review onboarding process | Operations | Farida Zaki | Medium | In Progress | 6000 | 1517 | 2024-07-16 | 2024-07-20 |  | 4 | 0 | Alexandria Logistics | Ahmed Nabil | 100000 | Operations | 200 | -4483 | -74.72% | N/A | Short (<=7 days) | Ahmed Nabil | On schedule
TSK-0191 | PRJ-010 | Product Line Expansion | Develop training material | Procurement | Tarek Abdelrahman | High | In Progress | 1500 | 814 | 2024-06-17 | 2024-06-28 |  | 11 | 0 | Internal | Sara Hassan | 150000 | IT | 180 | -686 | -45.73% | N/A | Medium (8-20 days) | Sara Hassan | On schedule
TSK-0080 | PRJ-004 | Warehouse Automation | Deploy inventory system | Procurement | Khaled Younes | High | In Progress | 2500 | 1859 | 2024-11-04 | 2024-11-23 |  | 19 | 0 | Cairo Financial Services | Laila Samir | 75000 | Finance | 280 | -641 | -25.64% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0306 | PRJ-015 | Data Center Upgrade | Develop database schema | Operations | Dina Fouad | High | Delayed | 1500 | 2034 | 2024-07-16 | 2024-07-22 | 2024-07-22 | 6 | 0 | Internal | Nourhan Tarek | 75000 | Marketing | 300 | 534 | 35.6% | N/A | Short (<=7 days) | Nourhan Tarek | On schedule
TSK-0244 | PRJ-012 | Cloud Migration | Procure warehouse layout | Quality | Farida Younes | Medium | Completed | 1000 | 1387 | 2024-02-21 | 2024-02-28 | 2024-03-01 | 7 | 2 | Red Sea Tourism | Ahmed Nabil | 250000 | Operations | 180 | 387 | 38.7% | Late | Short (<=7 days) | Ahmed Nabil | Delayed by 2 days
TSK-0298 | PRJ-015 | Data Center Upgrade | Design security policy | HR | Sherif Ibrahim | Low | Completed | 8000 | 8176 | 2024-08-01 | 2024-08-07 | 2024-08-09 | 6 | 2 | Internal | Nourhan Tarek | 75000 | Procurement | 180 | 176 | 2.2% | Late | Short (<=7 days) | Nourhan Tarek | Delayed by 2 days
TSK-0022 | PRJ-002 | ERP System Rollout | Install user interface | Operations | Sherif Ibrahim | High | Completed | 2500 | 0 | 2024-08-04 | 2024-08-31 | 2024-08-31 | 27 | 0 | Delta Retail Group | Youssef Adel | 150000 | Procurement | 180 | -2500 | -100% | On Time | Long (>20 days) | Youssef Adel | On schedule
TSK-0005 | PRJ-001 | Website Redesign | Install employee handbook | Quality | Sherif Hosny | Low | In Progress | 2000 | 734 | 2024-07-17 | 2024-08-02 |  | 16 | 0 | Nile Corp | Mona Farid | 75000 | Operations | 200 | -1266 | -63.3% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0125 | PRJ-006 | CRM Migration | Migrate hardware setup | IT | Dina Mahmoud | High | Pending | 2500 | 0 | 2024-06-25 | 2024-07-13 |  | 18 | 0 | BlueWave Telecom | Mona Farid | 120000 | Quality Assurance | 250 | -2500 | -100% | N/A | Medium (8-20 days) | Mona Farid | On schedule
TSK-0203 | PRJ-010 | Product Line Expansion | Document database schema | Quality | Khaled Naguib | Medium | Completed | 3000 | 2478 | 2024-08-03 | 2024-08-16 | 2024-08-16 | 13 | 0 | Internal | Sara Hassan | 150000 | Finance | 250 | -522 | -17.4% | On Time | Medium (8-20 days) | Sara Hassan | On schedule
TSK-0062 | PRJ-003 | Mobile App Launch | Review network infrastructure | IT | Yasmin Zaki | Medium | Behind Schedule | 6000 | 8019 | 2024-04-23 | 2024-05-16 | 2024-05-15 | 23 | -1 | Alexandria Logistics | Ahmed Nabil | 100000 | Operations | 220 | 2019 | 33.65% | N/A | Long (>20 days) | Ahmed Nabil | Early by 1 days
TSK-0300 | PRJ-015 | Data Center Upgrade | Document employee handbook | Quality | Mostafa El-Sayed | Low | In Progress | 2500 | 1721 | 2024-08-31 | 2024-09-24 |  | 24 | 0 | Internal | Nourhan Tarek | 75000 | Procurement | 200 | -779 | -31.16% | N/A | Long (>20 days) | Nourhan Tarek | On schedule
TSK-0142 | PRJ-007 | Network Security Overhaul | Migrate hardware setup | Finance | Ziad Abdelrahman | Low | In Progress | 10000 | 6223 |  |  |  |  | 0 | Internal | Laila Samir | 120000 | Finance | 220 | -3777 | -37.77% | N/A | Short (<=7 days) | Laila Samir | On schedule
TSK-0086 | PRJ-004 | Warehouse Automation | Audit employee handbook | HR | Sherif Ibrahim | Low | Ongoing | 5000 | 1387 | 2024-09-19 | 2024-10-01 |  | 12 | 0 | Cairo Financial Services | Laila Samir | 75000 | Procurement | 180 | -3613 | -72.26% | N/A | Medium (8-20 days) | Laila Samir | On schedule
TSK-0008 | PRJ-001 | Website Redesign | Approve vendor contract | HR | Mariam Kamal | High | Pending | 1500 | 0 |  |  |  |  | 0 | Nile Corp | Mona Farid | 75000 | Procurement | 180 | -1500 | -100% | N/A | Short (<=7 days) | Mona Farid | On schedule
TSK-0167 | PRJ-008 | Office Relocation | Plan hardware setup | Finance | Noor Naguib | Low | Completed | 4000 | 3786 | 2024-06-05 | 2024-06-26 | 2024-06-23 | 21 | -3 | Pharos Holdings | Nourhan Tarek | 300000 | Marketing | 280 | -214 | -5.35% | On Time | Long (>20 days) | Nourhan Tarek | Early by 3 days
TSK-0223 | PRJ-011 | HR System Implementation | Design training material | Marketing | Dina Mahmoud | High | Completed | 8000 | 7859 | 2024-03-12 | 2024-03-24 | 2024-03-26 | 12 | 2 | Giza Health Systems | Ahmed Nabil | 200000 | Quality Assurance | 250 | -141 | -1.762% | Late | Medium (8-20 days) | Ahmed Nabil | Delayed by 2 days
TSK-0121 | PRJ-006 | CRM Migration | Optimize security policy | Procurement | Mostafa El-Sayed | High | Completed | 4000 | 4692 | 2024-07-10 | 2024-07-23 | 2024-07-24 | 13 | 1 | BlueWave Telecom | Mona Farid | 120000 | Procurement | 200 | 692 | 17.3% | Late | Medium (8-20 days) | Mona Farid | Delayed by 1 days

## Tasks_RawData
Task_ID | Project_ID | Project_Name | Task_Name | Department | Assigned_To | Priority | Status | Start_Date | Planned_End_Date | Actual_End_Date | Planned_Cost | Actual_Cost
TSK-0085 | PRJ-004 | Warehouse Automation | Audit marketing collateral | FINANCE | Farida Hosny | MEDIUM | Delayed | 05-Jul-2024 | 02-Aug-2024 | 09-Aug-2024 | 1500 | 1396
TSK-0276 | PRJ-014 | Retail Store Opening | Develop backup procedure | Operations | Noor Naguib | high | in progress | 2024-05-23 | 2024-06-20 |  | 4000 | 1731
TSK-0216 | PRJ-011 | HR System Implementation | Procure warehouse layout | MARKETING | Khaled Younes | Low | IN PROGRESS | 2024/04/03 | 2024/04/30 |  | 1500 | 377
TSK-0122 | PRJ-006 | CRM Migration | Audit vendor contract | finance | Aya Ibrahim | medium | DELAYED | 06-29-2024 | 07-12-2024 | 07-24-2024 | 4000 | 4369
TSK-0299 | PRJ-015 | Data Center Upgrade | Configure supplier list | FINANCE | Dina Fouad | HIGH | IN PROGRESS | 04-Aug-2024 | 26-Aug-2024 |  | 4000 | 1678
TSK-0150 | PRJ-008 | Office Relocation | Develop training material | Finance | Mariam Kamal | high | Delayed | 07-20-2024 | 08-07-2024 | 08-12-2024 | 1000 | 1347
TSK-0303 | PRJ-015 | Data Center Upgrade | Plan hardware setup | FINANCE | Farida Shawky | M | Not Started | 2024/05/26 | 2024/06/16 |  | 10000 | 0
TSK-0058 | PRJ-003 | Mobile App Launch | Audit inventory system |  | Tarek Shawky | Medium | Not started | 20-Jul-2024 | 19-Aug-2024 |  | 1000 | 0
TSK-0014 | PRJ-001 | Website Redesign | Deploy inventory system | Operations | Farida Hosny | medium | In Progress | 14-Aug-2024 | 07-Sep-2024 |  | 1500 | 618
TSK-0090 | PRJ-005 | Customer Portal Upgrade | Optimize quality checklist | Marketing | Farida Zaki | L | Complete | 2024-02-19 | 2024-03-19 | 2024-03-17 | 10000 | 7969
TSK-0211 | PRJ-011 | HR System Implementation | Document training material | I.T. | Tarek Abdelrahman | H | In Progress | 30-Jun-2024 | 15-Jul-2024 |  | 4000 | 2110
TSK-0093 | PRJ-005 | Customer Portal Upgrade | Procure vendor contract | marketing | Dina Zaki | M | Complete | 2024/01/10 | 2024/01/15 | 2024/01/12 |  | 2553
TSK-0172 | PRJ-009 | Supply Chain Optimization | Audit user interface | QA | Farida Shawky | L | Completed | 20/05/2024 | 29/05/2024 | 29/05/2024 | 1500 | 1823
TSK-0153 | PRJ-008 | Office Relocation | Audit inventory system |  | Hassan Fouad | Med | Ongoing | 2024/04/13 | 2024/05/07 |  | 10000 | 5964
TSK-0053 | PRJ-003 | Mobile App Launch | Migrate API integration | I.T. | Farida Hosny | M | COMPLETED | 07-Jun-2024 | 30-Jun-2024 | 27-Jun-2024 | 4000 | 5187
TSK-0288 | PRJ-014 | Retail Store Opening | Optimize customer feedback survey | it | Salma Fouad | Low | COMPLETED | 22/02/2024 | 08/03/2024 | 10/03/2024 | 1000 | 1263
TSK-0038 | PRJ-002 | ERP System Rollout | Audit API integration | PROCUREMENT | Tarek Abdelrahman | HIGH | Not Started | 2024-08-09 | 2024-09-01 |  | 6000 | 0
TSK-0101 | PRJ-005 | Customer Portal Upgrade | Design network infrastructure | QA | Aya Ibrahim | Medium | Complete | 28/01/2024 | 21/02/2024 | 23/02/2024 | 5000 | 4772
TSK-0024 | PRJ-002 | ERP System Rollout | Migrate backup procedure | finance | Sherif Hosny | L | COMPLETED | 09-07-2024 | 09-18-2024 | 09-18-2024 | 1500 | 1799
TSK-0212 | PRJ-011 | HR System Implementation | Test backup procedure | I.T | Farida Younes | High | NOT STARTED | 2024-05-22 | 2024-05-30 |  | 5000 | 0
TSK-0204 | PRJ-010 | Product Line Expansion | Document warehouse layout | I.T. | Salma Fouad | high | Done | 2024-04-22 | 2024-05-02 | 2024-05-04 | 2500 | 2216
TSK-0317 |  |  | TEST - ignore
TSK-0104 | PRJ-005 | Customer Portal Upgrade | Install budget report | FINANCE | Noor Naguib | LOW | completed | 13/05/2024 | 22/05/2024 | 19/05/2024 | 2000 | 2594
TSK-0192 | PRJ-010 | Product Line Expansion | Analyze security policy | I.T. | Noor Naguib | MEDIUM | Not started | 2024-06-19 | 2024-06-24 |  | 8000 | 0
TSK-0245 | PRJ-012 | Cloud Migration | Test marketing collateral | marketing | Noor Naguib | Low | COMPLETED | 2024-02-26 | 2024-03-15 | 2024-03-15 | 1500 | 1982
TSK-0213 | PRJ-011 | HR System Implementation | Train users on hardware setup | Marketing | Reem Gaber | L | in progress | 05-Apr-2024 | 09-Apr-2024 |  | 1500 | 598
TSK-0149 | PRJ-008 | Office Relocation | Test API integration | Quality Assurance | Sherif Ibrahim | M | Not started | 26/06/2024 | 30/06/2024 |  | 1000 | 0
TSK-0198 | PRJ-010 | Product Line Expansion | Plan database schema | it |  | High | COMPLETED | 05-30-2024 | 06-13-2024 | 06-13-2024 | 8000 | 5874
TSK-0082 | PRJ-004 | Warehouse Automation | Audit budget report | MARKETING | Yasmin Younes | HIGH | Done | 10-29-2024 | 11-03-2024 | 11-02-2024 |  | 6098
TSK-0119 | PRJ-006 | CRM Migration | Document user interface | quality assurance | Ziad Abdelrahman | medium | Done | 08/07/2024 | 31/07/2024 | 02/08/2024 | 10000 | 12422
TSK-0304 | PRJ-015 | Data Center Upgrade | Approve budget report | Marketing | Khaled Naguib | LOW | Delayed | 02-Aug-2024 | 25-Aug-2024 | 26-Aug-2024 | 2000 | 2297
TSK-0048 | PRJ-003 | Mobile App Launch | Install vendor contract | IT | Salma Fouad | M | completed | 2024-03-01 | 2024-03-21 | 2024-03-21 | 1500 | 1286
TSK-0051 | PRJ-003 | Mobile App Launch | Approve onboarding process | HR | Mostafa El-Sayed | high | COMPLETED | 22-Jul-2024 | 06-Aug-2024 | 04-Aug-2024 | 5000 | 3653
TSK-0068 | PRJ-004 | Warehouse Automation | Review API integration | I.T. | Ziad Abdelrahman | HIGH | Done | 17-Oct-2024 | 09-Nov-2024 | 06-Nov-2024 | 1000 | 1399
TSK-0307 | PRJ-015 | Data Center Upgrade | Deploy server configuration | IT | Noor Naguib | H | in progress | 24/06/2024 | 04/07/2024 |  | 2500 | 1606
TSK-0017 | PRJ-001 | Website Redesign | Procure customer feedback survey | H.R. | Khaled Younes | medium | Delayed | 11-07-2024 | 11-18-2024 | 11-16-2024 | 1500 | 1676
TSK-0206 | PRJ-010 | Product Line Expansion | Configure network infrastructure | IT | Khaled Naguib | High | Pending | 2024/08/09 | 2024/08/27 |  | 1000 | 0
TSK-0117 | PRJ-006 | CRM Migration | Migrate server configuration | Marketing | Tarek Shawky | HIGH | Pending | 05-16-2024 | 05-24-2024 |  | 5000 | 0
TSK-0108 | PRJ-006 | CRM Migration | Deploy hardware setup | OPERATIONS | Farida Hosny | M | delayed | 05-07-2024 | 06-06-2024 | 06-05-2024 | 3000 | 2512
TSK-0196 | PRJ-010 | Product Line Expansion | Review network infrastructure | operations | Reem Gaber | MEDIUM | IN PROGRESS | 17/06/2024 | 04/07/2024 |  | 3000 | 1021
TSK-0305 | PRJ-015 | Data Center Upgrade | Plan training material | FINANCE | Noor Naguib | L | COMPLETED | 14-Jun-2024 | 01-Jul-2024 | 30-Jun-2024 | 10000 | 10647
TSK-0177 | PRJ-009 | Supply Chain Optimization | Migrate employee handbook | PROCUREMENT | Khaled Naguib | L | In Progress | 02-26-2024 | 03-13-2024 |  | 2500 | 1242
TSK-0137 | PRJ-007 | Network Security Overhaul | Develop inventory system | IT | Noor Naguib | Low | Complete | 2024/07/23 | 2024/08/01 | 2024/07/29 | 1500 | 1674
TSK-0210 | PRJ-011 | HR System Implementation | Analyze marketing collateral | Finance | Sherif Hosny | High | IN PROGRESS | 2024-05-20 | 2024-06-06 |  | 1000 | 359
TSK-0181 | PRJ-009 | Supply Chain Optimization | Deploy budget report | Ops | Ziad Abdelrahman | HIGH | Not Started | 05/04/2024 | 17/04/2024 |  | 2000 | 0
TSK-0176 | PRJ-009 | Supply Chain Optimization | Design budget report | Marketing | Khaled Naguib | M | Completed | 2024/03/13 | 2024/04/07 | 2024/04/06 | 6000 | 8191
TSK-0189 | PRJ-010 | Product Line Expansion | Plan quality checklist | HR | Dina Fouad | Low | Ongoing | 2024/08/02 | 2024/08/19 |  | 8000 | 3329
TSK-0138 | PRJ-007 | Network Security Overhaul | Document hardware setup | Operations | Tarek Shawky | HIGH | In Progress | 07-21-2024 | 08-19-2024 |  | 10000 | 3913
TSK-0061 | PRJ-003 | Mobile App Launch | Approve quality checklist | Q.A. | Khaled Younes | Medium | Behind Schedule | 06-07-2024 | 06-10-2024 | 06-15-2024 | 8000 | 6292
TSK-0067 | PRJ-004 | Warehouse Automation | Optimize dashboard | H.R. | Mostafa El-Sayed | high | NOT STARTED | 2024-10-07 | 2024-10-26 |  | 1500 | 0
TSK-0088 | PRJ-005 | Customer Portal Upgrade | Plan customer feedback survey | Finance | Dina Zaki | Low | Done | 04/04/2024 | 01/05/2024 | 02/05/2024 | 2000 | 2236
TSK-0037 | PRJ-002 | ERP System Rollout | Audit inventory system | Procurement | Salma Fouad | M | In Progress | 19/11/2024 | 11/12/2024 |  | 3000 | 2365
TSK-0266 | PRJ-013 | Brand Refresh Campaign | Review employee handbook | OPERATIONS | Hana Zaki | HIGH | Done | 14-Jul-2024 | 29-Jul-2024 | 29-Jul-2024 | 5000 | 5016
TSK-0070 | PRJ-004 | Warehouse Automation | Procure vendor contract | Quality Assurance | Noor Naguib | low | Behind Schedule | 10-Oct-2024 | 27-Oct-2024 | 31-Oct-2024 | 5000 | 4686
TSK-0205 | PRJ-010 | Product Line Expansion | Configure API integration | finance | Fady Hosny | MEDIUM | Ongoing | 04/04/2024 | 29/04/2024 |  | 4000 | 3074
TSK-0263 | PRJ-013 | Brand Refresh Campaign | Train users on employee handbook | IT | Tarek Abdelrahman | high | Complete | 11-Apr-2024 | 05-May-2024 | 04-May-2024 | 5000 | 6706
TSK-0248 | PRJ-012 | Cloud Migration | Review onboarding process | Operations | Mostafa El-Sayed | Medium | Done | 2024-05-30 | 2024-06-16 | 2024-06-15 | 1500 | 2080
TSK-0044 | PRJ-003 | Mobile App Launch | Design marketing collateral | HR | Sherif Hosny | H | Ongoing | 2024/05/19 | 2024/06/10 |  | 3000 | 647
TSK-0208 | PRJ-011 | HR System Implementation | Document warehouse layout | operations | Tarek Shawky | L | Complete | 05-16-2024 | 05-24-2024 | 05-26-2024 | 8000 | 9484
TSK-0277 | PRJ-014 | Retail Store Opening | Train users on onboarding process | procurement | Salma Fouad | low | COMPLETED | 2024-04-17 | 2024-05-10 | 2024-05-10 | 4000 | 4446
TSK-0291 | PRJ-014 | Retail Store Opening | Analyze quality checklist | Finance | Salma Fouad | Low | in progress | 2024/01/29 | 2024/02/03 |  | 8000 | 2966
TSK-0076 | PRJ-004 | Warehouse Automation | Optimize server configuration | Marketing | Tarek Abdelrahman | MEDIUM | Complete | 08-16-2024 | 09-12-2024 | 09-13-2024 | 1500 | 1412
TSK-0318 |  |  | TEST - ignore
TSK-0284 | PRJ-014 | Retail Store Opening | Document budget report | marketing | Farida Zaki | MEDIUM | Delayed | 10-Jun-2024 | 08-Jul-2024 | 23-Jul-2024 | 1500 | 1497
TSK-0297 | PRJ-015 | Data Center Upgrade | Deploy user interface | FINANCE | Dina Mahmoud | Med | Done | 2024/05/22 | 2024/06/18 | 2024/06/19 | 3000 | 2936
TSK-0259 | PRJ-013 | Brand Refresh Campaign | Plan server configuration | Q.A. | Hassan Fouad | low | COMPLETED | 20/05/2024 | 01/06/2024 | 01/06/2024 | 2000 | 2777
TSK-0006 | PRJ-001 | Website Redesign | Design onboarding process | HR | Farida Younes | H | delayed | 14-Oct-2024 | 01-Nov-2024 | 04-Nov-2024 | 5000 | 6659
TSK-0296 | PRJ-015 | Data Center Upgrade | Design employee handbook | finance | Hassan Fouad | LOW | in progress | 15-May-2024 | 11-Jun-2024 |  | 1500 | 408
TSK-0007 | PRJ-001 | Website Redesign | Develop backup procedure | MARKETING |  | L | Ongoing | 2024/07/21 | 2024/07/30 |  | 3000 | 992
TSK-0271 | PRJ-014 | Retail Store Opening | Deploy warehouse layout | finance | Tarek Shawky | HIGH | completed | 01-29-2024 | 02-07-2024 | 02-06-2024 | 6000 | 6093
TSK-0252 | PRJ-013 | Brand Refresh Campaign | Procure warehouse layout | PROCUREMENT | Yasmin Younes | M | Complete | 2024/08/08 | 2024/08/15 | 2024/08/15 | 1000 | 1071
TSK-0222 | PRJ-011 | HR System Implementation | Test security policy | Finance | Rania Gaber | high | Delayed | 2024/05/11 | 2024/06/06 | 2024/06/17 | 4000 | 3554
TSK-0201 | PRJ-010 | Product Line Expansion | Train users on dashboard | HR | Farida Younes | Medium | Complete | 07-03-2024 | 07-27-2024 | 07-27-2024 | 2000 | 1896
TSK-0207 | PRJ-010 | Product Line Expansion | Analyze onboarding process | QA | Khaled Younes | low | not started | 2024-04-25 | 2024-05-25 |  | 8000 | 0
TSK-0185 | PRJ-009 | Supply Chain Optimization | Develop onboarding process |  | Reem Gaber | Medium | in progress | 2024-01-06 | 2024-01-27 |  | 1500 | 312
TSK-0045 | PRJ-003 | Mobile App Launch | Procure backup procedure | Ops | Dina Fouad | medium | Complete | 07-25-2024 | 08-10-2024 | 08-12-2024 | 6000 | 8270
TSK-0218 | PRJ-011 | HR System Implementation | Train users on backup procedure | operations | Farida Shawky | H | completed | 16/03/2024 | 09/04/2024 | 09/04/2024 | 2500 | 3495
TSK-0196 | PRJ-010 | Product Line Expansion | Review network infrastructure | operations | Reem Gaber | MEDIUM | IN PROGRESS | 17/06/2024 | 04/07/2024 |  | 3000 | 1021
TSK-0190 | PRJ-010 | Product Line Expansion | Plan user interface | HR | Ziad Abdelrahman | High | Ongoing | 31/03/2024 | 10/04/2024 |  | 1000 | 483
TSK-0295 | PRJ-015 | Data Center Upgrade | Optimize security policy | Finance | Mostafa El-Sayed | MEDIUM | completed | 05/07/2024 | 14/07/2024 | 15/07/2024 | 3000 | 2484
TSK-0155 | PRJ-008 | Office Relocation | Approve database schema | Marketing | Tarek Shawky | Medium | Done | 03-03-2024 | 03-08-2024 | 03-07-2024 | 8000 | 6121
TSK-0109 | PRJ-006 | CRM Migration | Develop warehouse layout | Procurement | Hana Zaki | high | Done | 2024-05-21 | 2024-06-19 | 2024-06-20 | 1000 | 1278
TSK-0281 | PRJ-014 | Retail Store Opening | Plan backup procedure | HR | Yasmin El-Sayed | H | delayed | 02-17-2024 | 03-16-2024 | 03-31-2024 | 2000 | 2272
TSK-0144 | PRJ-007 | Network Security Overhaul | Approve warehouse layout | operations | Khaled Naguib | L | Pending | 06/08/2024 | 13/08/2024 |  | 2500 | 0
TSK-0077 | PRJ-004 | Warehouse Automation | Optimize supplier list | Marketing | Tarek Abdelrahman | high | NOT STARTED | 2024-08-26 | 2024-09-07 |  | 4000 | 0
TSK-0124 | PRJ-006 | CRM Migration | Develop vendor contract | H.R. | Sherif Hosny | low | Pending | 27/04/2024 | 01/05/2024 |  | 8000 | 0
TSK-0285 | PRJ-014 | Retail Store Opening | Procure quality checklist | MARKETING | Sherif Ibrahim | Low | In Progress | 05-24-2024 | 05-27-2024 |  | 5000 | 2964
TSK-0063 | PRJ-003 | Mobile App Launch | Deploy supplier list | Marketing |  | H | Pending | 2024/06/22 | 2024/07/06 |  | 8000
TSK-0023 | PRJ-002 | ERP System Rollout | Install training material | I.T. | Rania Gaber | LOW | Not started | 2024/10/29 | 2024/11/20 |  | 8000 | 0
TSK-0253 | PRJ-013 | Brand Refresh Campaign | Train users on onboarding process | Operations | Tarek Shawky | H | in progress | 22/06/2024 | 11/07/2024 |  | 5000 | 2256
TSK-0042 | PRJ-003 | Mobile App Launch | Configure supplier list | Finance | Aya Ibrahim | L | IN PROGRESS | 2024/03/16 | 2024/04/09 |  | 2500 | 1886
TSK-0261 | PRJ-013 | Brand Refresh Campaign | Test server configuration | H.R. | Farida Younes | LOW | Done | 2024/04/19 | 2024/05/17 | 2024/05/19 | 4000 | 4271
TSK-0229 | PRJ-011 | HR System Implementation | Optimize hardware setup | procurement | Mostafa El-Sayed | High | Ongoing | 2024-06-07 | 2024-07-01 |  | 4000 | 2434
TSK-0132 | PRJ-007 | Network Security Overhaul | Deploy training material | MARKETING | Fady Hosny | High | Pending | 2024/10/10 | 2024/10/29 |  | 2500 | 0
TSK-0270 | PRJ-013 | Brand Refresh Campaign | Train users on vendor contract | finance | Mariam Kamal | H | Pending | 2024-08-19 | 2024-08-24 |  | 3000 | 0
TSK-0112 | PRJ-006 | CRM Migration | Procure inventory system |  | Ziad Abdelrahman | high | Not started | 2024/03/20 | 2024/03/24 |  | 3000 | 0
TSK-0237 | PRJ-012 | Cloud Migration | Plan vendor contract | quality assurance | Hana Zaki | high | In Progress | 2024/03/21 | 2024/04/16 |  | 2000 | 653
TSK-0127 | PRJ-007 | Network Security Overhaul | Migrate training material | FINANCE |  | L | Done | 2024-06-26 | 2024-07-26 | 2024-07-27 | 6000 | 5346
TSK-0257 | PRJ-013 | Brand Refresh Campaign | Document employee handbook | QA | Mostafa El-Sayed | HIGH | Ongoing | 2024/07/25 | 2024/07/31 |  | 10000 | 7208
TSK-0030 | PRJ-002 | ERP System Rollout | Plan hardware setup | Procurement | Sherif Ibrahim | MEDIUM | completed | 2024-10-10 | 2024-10-18 | 2024-10-19 | 10000 | 13746
TSK-0032 | PRJ-002 | ERP System Rollout | Train users on customer feedback survey | IT | Rania Gaber | Med | Completed | 04/08/2024 | 20/08/2024 | 19/08/2024 | 6000 | 7171
TSK-0075 | PRJ-004 | Warehouse Automation | Plan customer feedback survey | Marketing | Yasmin Younes | MEDIUM | completed | 13/09/2024 | 10/10/2024 | 11/10/2024 | 10000 | 7595
TSK-0159 | PRJ-008 | Office Relocation | Design dashboard | hr | Farida Hosny | MEDIUM | IN PROGRESS | 26/03/2024 | 16/04/2024 |  | 2500 | 1388
TSK-0235 | PRJ-012 | Cloud Migration | Document quality checklist | IT | Farida Shawky | HIGH | IN PROGRESS | 07/06/2024 | 16/06/2024 |  | 1000 | 606
TSK-0238 | PRJ-012 | Cloud Migration | Install onboarding process | I.T. | Tarek Abdelrahman | Low | DELAYED | 05-Feb-2024 | 29-Feb-2024 | 29-Feb-2024 | 1000 | 734
TSK-0145 | PRJ-008 | Office Relocation | Develop budget report | Finance | Farida Hosny | medium | Delayed | 2024-05-26 | 2024-06-03 | 2024-06-04 | 8000 | 8335
TSK-0171 | PRJ-009 | Supply Chain Optimization | Review warehouse layout | OPERATIONS | Fady Hosny | LOW | not started | 14-Feb-2024 | 12-Mar-2024 |  | 6000 | 0
TSK-0059 | PRJ-003 | Mobile App Launch | Test hardware setup | Procurement | Mostafa El-Sayed | Low | completed | 08/03/2024 | 20/03/2024 | 20/03/2024 | 1000 | 1106
TSK-0131 | PRJ-007 | Network Security Overhaul | Document customer feedback survey | Ops | Salma Fouad | Med | Ongoing | 10/10/2024 | 28/10/2024 |  | 8000 | 5450
TSK-0236 | PRJ-012 | Cloud Migration | Deploy backup procedure | H.R. | Khaled Naguib |  | In Progress | 19-May-2024 | 14-Jun-2024 |  | 8000 | 4463
TSK-0186 | PRJ-009 | Supply Chain Optimization | Migrate onboarding process | HR | Reem Gaber | high | In Progress | 13/03/2024 | 18/03/2024 |  | 3000 | 742
TSK-0113 | PRJ-006 | CRM Migration | Test onboarding process | QA | Dina Fouad | high | DELAYED | 2024-07-01 | 2024-07-20 | 2024-07-31 | 6000 | 7892
TSK-0074 | PRJ-004 | Warehouse Automation | Deploy database schema | Finance | Ziad Abdelrahman | MEDIUM | IN PROGRESS | 2024-06-23 | 2024-07-01 |  | 2000 | 1080
TSK-0072 | PRJ-004 | Warehouse Automation | Configure network infrastructure | Procurement | Fady Hosny | Low | In Progress | 2024/09/03 | 2024/09/25 |  | 3000 | 1233
TSK-0139 | PRJ-007 | Network Security Overhaul | Migrate supplier list | hr | Khaled Younes | high | IN PROGRESS | 09-Sep-2024 | 29-Sep-2024 |  | 6000 | 1369
TSK-0071 | PRJ-004 | Warehouse Automation | Develop warehouse layout | FINANCE | Khaled Younes | High | Delayed | 13/07/2024 | 18/07/2024 | 28/07/2024 | 1500 | 1832
TSK-0273 | PRJ-014 | Retail Store Opening | Test database schema | Marketing | Farida Shawky | HIGH | Ongoing | 2024-02-16 | 2024-03-07 |  | 2500 | 895
TSK-0279 | PRJ-014 | Retail Store Opening | Design inventory system | HR | Farida Younes | Medium | Complete | 14-May-2024 | 07-Jun-2024 | 07-Jun-2024 | 6000 | 5085
TSK-0089 | PRJ-005 | Customer Portal Upgrade | Optimize security policy | Marketing | Sherif Hosny | M | in progress | 03-21-2024 | 04-17-2024 |  | 6000 | 2042
TSK-0173 | PRJ-009 | Supply Chain Optimization | Plan customer feedback survey | Quality Assurance | Tarek Shawky | high | In Progress | 31-May-2024 | 25-Jun-2024 |  | 4000 | 2867
TSK-0283 | PRJ-014 | Retail Store Opening | Procure quality checklist | IT | Dina Mahmoud | H | Completed | 14-Feb-2024 | 07-Mar-2024 | 08-Mar-2024 | 1000 | 1328
TSK-0003 | PRJ-001 | Website Redesign | Deploy warehouse layout | Procurement | Reem Gaber | Medium | In Progress | 2024/10/21 | 2024/10/31 |  | 3000 | 1804
TSK-0154 | PRJ-008 | Office Relocation | Analyze marketing collateral | Ops | Yasmin Zaki | L | completed | 17-May-2024 | 31-May-2024 | 28-May-2024 | 1500 | 1055
TSK-0162 | PRJ-008 | Office Relocation | Document dashboard | HR | Yasmin El-Sayed | Medium | DELAYED | 2024/02/28 | 2024/03/05 | 2024/03/10 | 2500 | 2644
TSK-0315 |  |  | TEST - ignore
TSK-0242 | PRJ-012 | Cloud Migration | Procure vendor contract | MARKETING | Mariam Kamal | high | In Progress | 02-03-2024 | 03-04-2024 |  | 3000 | 1248
TSK-0039 | PRJ-002 | ERP System Rollout | Deploy warehouse layout | I.T | Yasmin Younes | High | Delayed | 18/10/2024 | 05/11/2024 | 04/11/2024 | 10000 | 11406
TSK-0002 | PRJ-001 | Website Redesign | Document warehouse layout | procurement | Khaled Naguib | M | IN PROGRESS | 2024-10-05 | 2024-10-11 |  | 2500 | 837
TSK-0264 | PRJ-013 | Brand Refresh Campaign | Plan employee handbook | H.R. | Hassan Fouad | Med | Done | 2024-04-12 | 2024-04-24 | 2024-04-26 | 2500 | 2311
TSK-0035 | PRJ-002 | ERP System Rollout | Audit warehouse layout | procurement | Ziad Abdelrahman | L | completed | 10/11/2024 | 27/11/2024 | 24/11/2024 | 1500 | 1359
TSK-0201 | PRJ-010 | Product Line Expansion | Train users on dashboard | HR | Farida Younes | Medium | Complete | 07-03-2024 | 07-27-2024 | 07-27-2024 | 2000 | 1896
TSK-0247 | PRJ-012 | Cloud Migration | Document employee handbook | it | Farida Zaki | medium | Complete | 2024-02-12 | 2024-03-10 | 2024-03-10 | 4000
TSK-0226 | PRJ-011 | HR System Implementation | Design inventory system | operations | Dina Zaki | L | COMPLETED | 05/07/2024 | 08/07/2024 | 10/07/2024 | 1000 | 1032
TSK-0265 | PRJ-013 | Brand Refresh Campaign | Install backup procedure | operations | Dina Zaki | high | Delayed | 2024-08-16 | 2024-09-14 | 2024-09-24 | 1500 | 1834
TSK-0102 | PRJ-005 | Customer Portal Upgrade | Deploy dashboard |  | Yasmin Younes |  | not started | 2024/04/10 | 2024/04/25 |  | 10000 | 0
TSK-0115 | PRJ-006 | CRM Migration | Train users on customer feedback survey | Finance | Yasmin El-Sayed | low | Ongoing | 27-May-2024 | 16-Jun-2024 |  | 3000 | 732
TSK-0116 | PRJ-006 | CRM Migration | Develop user interface | I.T. | Yasmin El-Sayed | LOW | IN PROGRESS | 2024-04-01 | 2024-04-10 |  | 10000 | 5055
TSK-0200 | PRJ-010 | Product Line Expansion | Review user interface | IT | Salma Fouad | High | Completed | 05-17-2024 | 06-09-2024 | 06-09-2024 |  | 1529
TSK-0316 |  |  | TEST - ignore
TSK-0097 | PRJ-005 | Customer Portal Upgrade | Audit security policy | Procurement | Noor Naguib | L | Complete | 2024-02-24 | 2024-03-23 | 2024-03-21 | 1500 | 1802
TSK-0301 | PRJ-015 | Data Center Upgrade | Audit marketing collateral | operations | Khaled Naguib | H | Completed | 11-Aug-2024 | 18-Aug-2024 | 20-Aug-2024 | 8000 | 8590
TSK-0140 | PRJ-007 | Network Security Overhaul | Deploy onboarding process | Operations | Farida Hosny | medium | completed | 2024/09/18 | 2024/09/22 | 2024/09/23 | 5000 | 6887
TSK-0241 | PRJ-012 | Cloud Migration | Test vendor contract | procurement | Dina Zaki | High | In Progress | 2024-02-21 | 2024-03-21 |  | 10000 | 6014
TSK-0243 | PRJ-012 | Cloud Migration | Review onboarding process | IT | Khaled Naguib | MEDIUM | delayed | 15/05/2024 | 06/06/2024 | 11/06/2024 |  | 1441
TSK-0111 | PRJ-006 | CRM Migration | Deploy quality checklist | Marketing | Khaled Younes | M | completed | 01-Apr-2024 | 14-Apr-2024 | 16-Apr-2024 | 4000 | 4856
TSK-0106 | PRJ-005 | Customer Portal Upgrade | Approve API integration | Marketing | Hassan Fouad | Med | Ongoing | 05-29-2024 | 06-05-2024 |  | 10000 | 7305
TSK-0280 | PRJ-014 | Retail Store Opening | Design hardware setup | operations | Ziad Abdelrahman | low | Completed | 2024/01/26 | 2024/02/03 | 2024/02/02 | 2000 | 2123
TSK-0084 | PRJ-004 | Warehouse Automation | Install dashboard | I.T. | Yasmin Younes | Low | NOT STARTED | 29/10/2024 | 21/11/2024 |  | 2000 | 0
TSK-0193 | PRJ-010 | Product Line Expansion | Design supplier list | PROCUREMENT | Sherif Hosny | L | IN PROGRESS | 17/05/2024 | 12/06/2024 |  | 8000 | 5250
TSK-0310 | PRJ-015 | Data Center Upgrade | Design supplier list | IT | Dina Fouad | MEDIUM | completed | 08-04-2024 | 08-24-2024 | 08-21-2024 | 6000 | 8177
TSK-0091 | PRJ-005 | Customer Portal Upgrade | Analyze database schema | Quality Assurance | Sherif Hosny | Med | in progress | 19-May-2024 | 26-May-2024 |  | 5000 | 1275
TSK-0114 | PRJ-006 | CRM Migration | Deploy marketing collateral | Operations | Tarek Abdelrahman | Med | In Progress | 24-Jun-2024 | 06-Jul-2024 |  | 8000 | 1639
TSK-0217 | PRJ-011 | HR System Implementation | Deploy vendor contract | Marketing | Sherif Ibrahim | low | Delayed | 2024-06-25 | 2024-07-07 | 2024-07-06 | 5000 | 6660
TSK-0041 | PRJ-002 | ERP System Rollout | Plan database schema | Procurement | Farida Hosny | low | delayed | 2024-09-13 | 2024-10-07 | 2024-10-06 | 2000 | 1736
TSK-0087 | PRJ-004 | Warehouse Automation | Optimize security policy | quality assurance | Reem Gaber | H | Done | 10-30-2024 | 11-13-2024 | 11-10-2024 | 4000 | 3665
TSK-0130 | PRJ-007 | Network Security Overhaul | Review hardware setup | procurement | Sherif Ibrahim | Low | Completed | 09-19-2024 | 10-01-2024 | 09-29-2024 | 5000
TSK-0103 | PRJ-005 | Customer Portal Upgrade | Optimize server configuration | Quality Assurance | Hana Zaki | Med | Done | 29/03/2024 | 21/04/2024 | 20/04/2024 | 2500 | 3431
TSK-0302 | PRJ-015 | Data Center Upgrade | Analyze quality checklist | Marketing | Khaled Naguib | HIGH | Completed | 08-05-2024 | 09-03-2024 | 09-05-2024 | 1500 | 1522
TSK-0308 | PRJ-015 | Data Center Upgrade | Plan warehouse layout | procurement | Sherif Ibrahim | Med | DELAYED | 2024/08/22 | 2024/09/02 | 2024/09/16 | 6000 | 4767
TSK-0043 | PRJ-003 | Mobile App Launch | Install hardware setup | OPERATIONS | Noor Naguib | high | Completed | 2024-05-15 | 2024-06-06 | 2024-06-08 | 10000 | 13448
TSK-0027 | PRJ-002 | ERP System Rollout | Design budget report |  | Ziad Abdelrahman | low | In Progress | 2024/11/04 | 2024/11/11 |  | 10000 | 5205
TSK-0110 | PRJ-006 | CRM Migration | Audit dashboard | HR | Aya Ibrahim | M | Completed | 09-May-2024 | 01-Jun-2024 | 31-May-2024 | 6000 | 5228
TSK-0118 | PRJ-006 | CRM Migration | Optimize marketing collateral | PROCUREMENT | Mostafa El-Sayed | MEDIUM | In Progress | 2024-03-24 | 2024-04-09 |  | 10000 | 3846
TSK-0092 | PRJ-005 | Customer Portal Upgrade | Deploy network infrastructure | finance | Farida Shawky | medium | In Progress | 01-16-2024 | 01-29-2024 |  | 1500 | 1055
TSK-0148 | PRJ-008 | Office Relocation | Audit budget report | H.R. | Sherif Ibrahim | Medium | COMPLETED | 31/05/2024 | 15/06/2024 | 15/06/2024 | 10000 | 8702
TSK-0202 | PRJ-010 | Product Line Expansion | Document employee handbook | hr | Rania Gaber | M | Complete | 28/07/2024 | 01/08/2024 | 29/07/2024 | 3000 | 2904
TSK-0230 | PRJ-011 | HR System Implementation | Audit training material | Marketing | Mariam Kamal | HIGH | Done | 04-21-2024 | 05-15-2024 | 05-16-2024 | 6000 | 8007
TSK-0282 | PRJ-014 | Retail Store Opening | Review training material | it | Salma Fouad | High | in progress | 03/03/2024 | 22/03/2024 |  | 8000
TSK-0170 | PRJ-009 | Supply Chain Optimization | Plan budget report | Ops | Noor Naguib | L | Behind Schedule | 15-Apr-2024 | 09-May-2024 | 21-May-2024 | 5000 | 5985
TSK-0309 | PRJ-015 | Data Center Upgrade | Analyze supplier list | PROCUREMENT | Noor Naguib | MEDIUM | Ongoing | 08-07-2024 | 08-27-2024 |  | 2500 | 1707
TSK-0234 | PRJ-012 | Cloud Migration | Approve supplier list | finance | Farida Shawky | low | completed | 28-May-2024 | 25-Jun-2024 | 22-Jun-2024 | 2000 | 2260
TSK-0161 | PRJ-008 | Office Relocation | Document quality checklist | HR | Hassan Fouad | Low | Complete | 2024-05-28 | 2024-06-22 | 2024-06-23 | 10000 | 11467
TSK-0146 | PRJ-008 | Office Relocation | Optimize API integration | Quality Assurance | Yasmin Younes | high | in progress | 2024/02/28 | 2024/03/08 |  | 8000 | 3789
TSK-0064 | PRJ-003 | Mobile App Launch | Analyze user interface | HR | Tarek Abdelrahman | HIGH | DELAYED | 04-22-2024 | 05-09-2024 | 05-20-2024 | 2500 | 3247
TSK-0221 | PRJ-011 | HR System Implementation | Design backup procedure | HR | Farida Zaki | low | NOT STARTED | 03-08-2024 | 04-03-2024 |  | 6000 | 0
TSK-0219 | PRJ-011 | HR System Implementation | Procure vendor contract | IT | Hana Zaki | LOW | In Progress | 2024/05/05 | 2024/05/24 |  | 6000 | 4502
TSK-0228 | PRJ-011 | HR System Implementation | Train users on marketing collateral | procurement | Farida Zaki | LOW | Done | 05-11-2024 | 06-04-2024 | 06-01-2024 | 6000 | 4468
TSK-0255 | PRJ-013 | Brand Refresh Campaign | Procure employee handbook | procurement | Farida Hosny | low | delayed | 07-Aug-2024 | 27-Aug-2024 | 03-Sep-2024 | 1500 | 1849
TSK-0293 | PRJ-014 | Retail Store Opening | Optimize vendor contract | FINANCE | Fady Hosny | L | Complete | 2024-03-14 | 2024-04-10 | 2024-04-09 | 6000 | 7063
TSK-0137 | PRJ-007 | Network Security Overhaul | Develop inventory system | IT | Noor Naguib | Low | Complete | 2024/07/23 | 2024/08/01 | 2024/07/29 | 1500 | 1674
TSK-0060 | PRJ-003 | Mobile App Launch | Install budget report | operations | Khaled Naguib | LOW | COMPLETED | 2024-04-09 | 2024-04-20 | 2024-04-20 | 3000 | 3668
TSK-0227 | PRJ-011 | HR System Implementation | Approve warehouse layout | FINANCE |  | Med | In Progress | 2024/04/29 | 2024/05/08 |  | 6000 | 2288
TSK-0241 | PRJ-012 | Cloud Migration | Test vendor contract | procurement | Dina Zaki | High | In Progress | 2024-02-21 | 2024-03-21 |  | 10000 | 6014
TSK-0133 | PRJ-007 | Network Security Overhaul | Install hardware setup | it | Fady Hosny | H | Complete | 2024-06-06 | 2024-06-23 | 2024-06-21 | 8000 | 7926
TSK-0056 | PRJ-003 | Mobile App Launch | Plan budget report | hr | Mariam Kamal | MEDIUM | IN PROGRESS | 2024/02/29 | 2024/03/28 |  | 6000 | 4444
TSK-0020 | PRJ-002 | ERP System Rollout | Test hardware setup | Ops | Aya Ibrahim | LOW | Done | 04/11/2024 | 21/11/2024 | 21/11/2024 | 2500 | 2645
TSK-0078 | PRJ-004 | Warehouse Automation | Procure warehouse layout | Procurement | Khaled Naguib | H | COMPLETED | 2024/07/02 | 2024/07/18 | 2024/07/15 | 6000 | 8069
TSK-0209 | PRJ-011 | HR System Implementation | Document warehouse layout | PROCUREMENT | Tarek Shawky | Low | in progress | 07-20-2024 | 08-04-2024 |  | 10000 | 2194
TSK-0267 | PRJ-013 | Brand Refresh Campaign | Audit dashboard | IT | Tarek Shawky |  | Not Started | 2024-04-28 | 2024-05-10 |  | 3000
TSK-0292 | PRJ-014 | Retail Store Opening | Audit backup procedure | hr | Hassan Fouad | Low | Complete | 2024/03/18 | 2024/03/26 | 2024/03/26 | 8000 | 6196
TSK-0136 | PRJ-007 | Network Security Overhaul | Train users on security policy | Operations | Khaled Younes | M | COMPLETED | 08/09/2024 | 28/09/2024 | 28/09/2024 | 2500 | 2183
TSK-0289 | PRJ-014 | Retail Store Opening | Develop training material | OPERATIONS | Yasmin Zaki | L | Not Started | 2024/04/23 | 2024/05/15 |  | 8000 | 0
TSK-0158 | PRJ-008 | Office Relocation | Migrate hardware setup | MARKETING | Farida Younes | HIGH | Ongoing | 18-May-2024 | 09-Jun-2024 |  | 2500 | 1219
TSK-0015 | PRJ-001 | Website Redesign | Approve user interface | quality assurance | Sherif Ibrahim | HIGH | Delayed | 2024-09-25 | 2024-10-23 | 2024-10-27 | 3000 | 2434
TSK-0182 | PRJ-009 | Supply Chain Optimization | Deploy vendor contract | Procurement | Hassan Fouad | low | in progress | 2024-04-16 | 2024-05-08 |  | 6000 | 4296
TSK-0262 | PRJ-013 | Brand Refresh Campaign | Optimize employee handbook | Marketing | Dina Mahmoud | LOW | in progress | 2024/06/24 | 2024/07/08 |  | 3000 | 993
TSK-0107 | PRJ-006 | CRM Migration | Develop vendor contract | OPERATIONS | Dina Zaki |  | Complete | 23-May-2024 | 30-May-2024 | 31-May-2024 | 10000 | 8274
TSK-0313 | PRJ-015 | Data Center Upgrade | Plan vendor contract | Marketing | Farida Hosny | medium | Ongoing | 2024-06-27 | 2024-06-30 |  | 2000 | 460
TSK-0143 | PRJ-007 | Network Security Overhaul | Analyze backup procedure | FINANCE | Khaled Naguib | Med | Ongoing | 17/06/2024 | 15/07/2024 |  | 6000 | 3942
TSK-0093 | PRJ-005 | Customer Portal Upgrade | Procure vendor contract | marketing | Dina Zaki | M | Complete | 2024/01/10 | 2024/01/15 | 2024/01/12 | 3000 | 2553
TSK-0016 | PRJ-001 | Website Redesign | Analyze server configuration | Q.A. | Hassan Fouad | High | in progress | 07-31-2024 | 08-15-2024 |  | 4000 | 1469
TSK-0164 | PRJ-008 | Office Relocation | Design backup procedure | Operations | Sherif Ibrahim | H | Complete | 2024-06-20 | 2024-07-03 | 2024-06-30 | 3000 | 2194
TSK-0029 | PRJ-002 | ERP System Rollout | Design customer feedback survey | IT | Sherif Hosny | High | NOT STARTED | 18/07/2024 | 14/08/2024 |  | 1000 | 0
TSK-0287 | PRJ-014 | Retail Store Opening | Document dashboard | Finance | Mariam Kamal | LOW | IN PROGRESS | 2024-04-22 | 2024-05-18 |  | 2000 | 1426
TSK-0220 | PRJ-011 | HR System Implementation | Optimize user interface | HR | Dina Fouad | HIGH | Behind Schedule | 2024/07/11 | 2024/07/25 | 2024/08/04 | 3000 | 2904
TSK-0168 | PRJ-009 | Supply Chain Optimization | Approve supplier list | Finance | Dina Zaki | HIGH | In Progress | 2024/02/07 | 2024/02/26 |  | 5000 | 2255
TSK-0054 | PRJ-003 | Mobile App Launch | Design user interface | it | Sherif Ibrahim | High | COMPLETED | 06-17-2024 | 06-23-2024 | 06-25-2024 | 1500 | 1516
TSK-0004 | PRJ-001 | Website Redesign | Review user interface | Marketing | Mostafa El-Sayed | L | In Progress | 2024-09-10 | 2024-09-26 |  | 5000 | 2401
TSK-0019 | PRJ-001 | Website Redesign | Audit onboarding process | Finance | Farida Younes | low | IN PROGRESS | 2024/07/31 | 2024/08/16 |  | 5000 | 3032
TSK-0290 | PRJ-014 | Retail Store Opening | Plan budget report | Operations | Farida Shawky | low | In Progress | 2024-02-24 | 2024-03-19 |  | 1000 | 416
TSK-0156 | PRJ-008 | Office Relocation | Test training material | IT | Dina Fouad | low | delayed | 02/06/2024 | 10/06/2024 | 11/06/2024 | 3000 | 2732
TSK-0057 | PRJ-003 | Mobile App Launch | Document onboarding process | H.R. | Dina Fouad | LOW | Complete | 2024-06-22 | 2024-07-22 | 2024-07-21 | 2500 | 3499
TSK-0094 | PRJ-005 | Customer Portal Upgrade | Document network infrastructure | IT | Hana Zaki | Medium | Ongoing | 2024/02/06 | 2024/03/06 |  | 6000 | 3348
TSK-0013 | PRJ-001 | Website Redesign | Develop quality checklist | finance | Sherif Ibrahim | L | Done | 02/11/2024 | 05/11/2024 | 03/11/2024 | 1500 | 2042
TSK-0066 | PRJ-003 | Mobile App Launch | Review database schema | hr | Aya Ibrahim | medium | completed | 27/02/2024 | 09/03/2024 | 07/03/2024 | 2000 | 2156
TSK-0269 | PRJ-013 | Brand Refresh Campaign | Deploy training material | IT | Farida Shawky | Low | Complete | 2024/06/18 | 2024/06/27 | 2024/06/29 | 4000 | 3393
TSK-0180 | PRJ-009 | Supply Chain Optimization | Review supplier list | IT | Sherif Ibrahim | high | In Progress | 05-13-2024 | 06-06-2024 |  | 6000 | 1233
TSK-0160 | PRJ-008 | Office Relocation | Approve budget report | QA | Dina Zaki | Med | Completed | 01-Apr-2024 | 24-Apr-2024 | 23-Apr-2024 |  | 2192
TSK-0254 | PRJ-013 | Brand Refresh Campaign | Configure security policy | marketing | Sherif Ibrahim | LOW | Pending | 2024/08/19 | 2024/09/18 |  | 4000 | 0
TSK-0126 | PRJ-007 | Network Security Overhaul | Develop database schema | PROCUREMENT | Farida Younes | H | In Progress | 07-07-2024 | 07-11-2024 |  | 5000 | 3364
TSK-0239 | PRJ-012 | Cloud Migration | Procure vendor contract | Procurement | Tarek Shawky | Med | In Progress | 18/02/2024 | 13/03/2024 |  | 8000 | 2896
TSK-0100 | PRJ-005 | Customer Portal Upgrade | Plan dashboard | quality assurance | Sherif Ibrahim | High | COMPLETED | 01-Apr-2024 | 25-Apr-2024 | 24-Apr-2024 | 3000 | 3036
TSK-0215 | PRJ-011 | HR System Implementation | Analyze training material | Marketing | Khaled Younes | Med | In Progress | 02-May-2024 | 07-May-2024 |  | 8000 | 3460
TSK-0075 | PRJ-004 | Warehouse Automation | Plan customer feedback survey | Marketing | Yasmin Younes | MEDIUM | completed | 13/09/2024 | 10/10/2024 | 11/10/2024 | 10000 | 7595
TSK-0147 | PRJ-008 | Office Relocation | Review vendor contract | Marketing | Aya Ibrahim | LOW | NOT STARTED | 01/03/2024 | 20/03/2024 |  | 5000 | 0
TSK-0232 | PRJ-012 | Cloud Migration | Audit supplier list | Marketing | Ziad Abdelrahman | Low | Done | 2024/05/23 | 2024/06/01 | 2024/06/02 | 1500 | 1961
TSK-0026 | PRJ-002 | ERP System Rollout | Document API integration | Quality Assurance | Salma Fouad | Med | Behind Schedule | 09-Jul-2024 | 23-Jul-2024 | 29-Jul-2024 | 5000 | 6487
TSK-0050 | PRJ-003 | Mobile App Launch | Deploy dashboard | MARKETING | Mariam Kamal | Medium | Behind Schedule | 09-May-2024 | 04-Jun-2024 | 10-Jun-2024 | 10000 | 11059
TSK-0037 | PRJ-002 | ERP System Rollout | Audit inventory system | Procurement | Salma Fouad | M | In Progress | 19/11/2024 | 11/12/2024 |  | 3000 | 2365
TSK-0028 | PRJ-002 | ERP System Rollout | Train users on supplier list | marketing | Dina Mahmoud | medium | Not started | 01-Nov-2024 | 14-Nov-2024 |  | 4000 | 0
TSK-0052 | PRJ-003 | Mobile App Launch | Deploy supplier list | Procurement | Noor Naguib | HIGH | Completed | 2024-03-23 | 2024-04-22 | 2024-04-22 | 1500 | 1602
TSK-0009 | PRJ-001 | Website Redesign | Audit dashboard | HR | Ziad Abdelrahman | LOW | Complete | 17/08/2024 | 26/08/2024 | 28/08/2024 | 4000 | 3468
TSK-0224 | PRJ-011 | HR System Implementation | Review database schema | Quality Assurance | Yasmin El-Sayed | HIGH | In Progress | 15-Apr-2024 | 26-Apr-2024 |  | 4000 | 2776
TSK-0312 | PRJ-015 | Data Center Upgrade | Test training material | Operations | Rania Gaber | LOW | Done | 17/06/2024 | 10/07/2024 | 12/07/2024 | 8000 | 10129
TSK-0034 | PRJ-002 | ERP System Rollout | Design server configuration | I.T. | Tarek Shawky | medium | delayed | 10-06-2024 | 11-03-2024 | 11-08-2024 | 4000 | 3583
TSK-0214 | PRJ-011 | HR System Implementation | Configure training material | Marketing | Tarek Abdelrahman | H | IN PROGRESS | 2024-03-18 | 2024-03-30 |  | 10000 | 4882
TSK-0012 | PRJ-001 | Website Redesign | Develop database schema | finance | Salma Fouad | L | COMPLETED | 08-15-2024 | 09-14-2024 | 09-11-2024 | 1500 | 1716
TSK-0018 | PRJ-001 | Website Redesign | Migrate vendor contract | hr | Khaled Naguib |  | In Progress | 2024/09/13 | 2024/09/29 |  | 1500 | 1154
TSK-0169 | PRJ-009 | Supply Chain Optimization | Develop quality checklist | PROCUREMENT | Noor Naguib | low | delayed | 2024/05/06 | 2024/05/18 | 2024/05/19 | 2000 | 1840
TSK-0134 | PRJ-007 | Network Security Overhaul | Optimize user interface | Quality Assurance | Yasmin Younes | High | Done | 2024-09-08 | 2024-09-22 | 2024-09-24 | 1500 | 1618
TSK-0025 | PRJ-002 | ERP System Rollout | Develop security policy | operations | Noor Naguib | low | in progress | 24-Jul-2024 | 09-Aug-2024 |  | 5000 | 1993
TSK-0029 | PRJ-002 | ERP System Rollout | Design customer feedback survey | IT | Sherif Hosny | High | NOT STARTED | 18/07/2024 | 14/08/2024 |  | 1000 | 0
TSK-0246 | PRJ-012 | Cloud Migration | Deploy employee handbook | quality assurance | Mariam Kamal | Low | DELAYED | 13-May-2024 | 06-Jun-2024 | 10-Jun-2024 | 6000 | 5652
TSK-0258 | PRJ-013 | Brand Refresh Campaign | Train users on security policy | QA | Yasmin Younes | Med | Completed | 2024-07-16 | 2024-08-13 | 2024-08-15 | 4000 | 5504
TSK-0105 | PRJ-005 | Customer Portal Upgrade | Review security policy | FINANCE | Yasmin El-Sayed | LOW | Done | 25/03/2024 | 24/04/2024 | 22/04/2024 | 2000 | 2511
TSK-0274 | PRJ-014 | Retail Store Opening | Audit network infrastructure | Q.A. | Sherif Hosny | HIGH | completed | 2024/05/30 | 2024/06/19 | 2024/06/19 | 2000 | 1912
TSK-0073 | PRJ-004 | Warehouse Automation | Design customer feedback survey | I.T | Salma Fouad | HIGH | COMPLETED | 2024/11/15 | 2024/11/25 | 2024/11/25 | 8000 | 11057
TSK-0157 | PRJ-008 | Office Relocation | Migrate customer feedback survey | Marketing | Hana Zaki | L | in progress | 16-Apr-2024 | 03-May-2024 |  | 1500 | 422
TSK-0040 | PRJ-002 | ERP System Rollout | Audit warehouse layout | Operations | Fady Hosny | low | Complete | 18-Nov-2024 | 03-Dec-2024 | 03-Dec-2024 | 6000 | 5449
TSK-0099 | PRJ-005 | Customer Portal Upgrade | Test supplier list | Marketing | Yasmin El-Sayed | medium | Delayed | 05-15-2024 | 06-09-2024 | 06-21-2024 | 4000 | 5388
TSK-0197 | PRJ-010 | Product Line Expansion | Plan hardware setup | Finance | Tarek Abdelrahman | H | NOT STARTED | 2024-06-14 | 2024-07-01 |  | 3000 | 0
TSK-0311 | PRJ-015 | Data Center Upgrade | Approve inventory system | Quality Assurance | Farida Shawky | M | completed | 26-Jul-2024 | 10-Aug-2024 | 08-Aug-2024 | 2000 | 2401
TSK-0175 | PRJ-009 | Supply Chain Optimization | Optimize network infrastructure | I.T | Mariam Kamal | low | delayed | 05-Mar-2024 | 12-Mar-2024 | 19-Mar-2024 | 2500 | 3083
TSK-0268 | PRJ-013 | Brand Refresh Campaign | Design employee handbook | I.T. | Aya Ibrahim | H | in progress | 08-18-2024 | 08-30-2024 |  | 2000 | 758
TSK-0049 | PRJ-003 | Mobile App Launch | Deploy budget report | procurement | Reem Gaber |  | COMPLETED | 2024/06/26 | 2024/07/06 | 2024/07/06 | 8000 | 6410
TSK-0199 | PRJ-010 | Product Line Expansion | Approve quality checklist | hr | Dina Zaki | High | Not Started | 31/03/2024 | 04/04/2024 |  | 2500 | 0
TSK-0033 | PRJ-002 | ERP System Rollout | Install warehouse layout | Marketing | Noor Naguib | MEDIUM | Ongoing | 08/09/2024 | 07/10/2024 |  | 1500 | 551
TSK-0165 | PRJ-008 | Office Relocation | Plan supplier list | operations | Farida Shawky | HIGH | Done | 18/07/2024 | 03/08/2024 | 03/08/2024 | 2500 | 3146
TSK-0123 | PRJ-006 | CRM Migration | Optimize security policy | MARKETING | Farida Shawky | Medium | delayed | 05-08-2024 | 06-02-2024 | 06-01-2024 | 4000 | 5387
TSK-0187 | PRJ-009 | Supply Chain Optimization | Develop hardware setup | PROCUREMENT | Tarek Abdelrahman | L | COMPLETED | 03-Mar-2024 | 07-Mar-2024 | 05-Mar-2024 | 1500 | 2021
TSK-0010 | PRJ-001 | Website Redesign | Document quality checklist | IT | Khaled Younes | High | Done | 2024-10-27 | 2024-11-05 | 2024-11-06 | 3000 | 2378
TSK-0095 | PRJ-005 | Customer Portal Upgrade | Design onboarding process | finance | Aya Ibrahim | Low | completed | 2024/05/22 | 2024/06/05 | 2024/06/02 | 8000 | 8647
TSK-0195 | PRJ-010 | Product Line Expansion | Test warehouse layout | Operations | Salma Fouad | Medium | IN PROGRESS | 23-Aug-2024 | 29-Aug-2024 |  | 8000 | 2241
TSK-0260 | PRJ-013 | Brand Refresh Campaign | Migrate customer feedback survey | FINANCE | Yasmin Younes | Medium | Pending | 24/06/2024 | 11/07/2024 |  | 2000 | 0
TSK-0001 | PRJ-001 | Website Redesign | Configure employee handbook | I.T. | Tarek Shawky | high | Done | 11-Oct-2024 | 31-Oct-2024 | 29-Oct-2024 | 3000 | 3208
TSK-0233 | PRJ-012 | Cloud Migration | Plan backup procedure | operations | Dina Fouad | medium | Ongoing | 04-13-2024 | 05-13-2024 |  | 2000 | 1335
TSK-0188 | PRJ-010 | Product Line Expansion | Review database schema | IT | Dina Zaki | H | Completed | 06-24-2024 | 07-13-2024 | 07-14-2024 | 3000 | 2451
TSK-0135 | PRJ-007 | Network Security Overhaul | Plan employee handbook | Ops | Khaled Younes | Med | In Progress | 2024-08-27 | 2024-09-01 |  | 8000 | 2238
TSK-0152 | PRJ-008 | Office Relocation | Approve backup procedure | PROCUREMENT | Khaled Naguib | High | NOT STARTED | 2024/06/16 | 2024/06/26 |  | 1500 | 0
TSK-0231 | PRJ-012 | Cloud Migration | Procure backup procedure | Finance | Mostafa El-Sayed | low | COMPLETED | 04-18-2024 | 05-11-2024 | 05-08-2024 | 2500 | 2372
TSK-0314 | PRJ-015 | Data Center Upgrade | Analyze dashboard | Marketing | Aya Ibrahim | H | in progress | 31-May-2024 | 13-Jun-2024 |  | 5000 | 1935
TSK-0272 | PRJ-014 | Retail Store Opening | Optimize dashboard | marketing | Dina Zaki | H | not started | 03-22-2024 | 04-20-2024 |  | 4000 | 0
TSK-0036 | PRJ-002 | ERP System Rollout | Migrate vendor contract | Finance | Mostafa El-Sayed | MEDIUM | Behind Schedule | 01/11/2024 | 12/11/2024 | 18/11/2024 | 3000 | 2584
TSK-0083 | PRJ-004 | Warehouse Automation | Configure backup procedure | IT | Aya Ibrahim | M | Complete | 2024/11/10 | 2024/12/08 | 2024/12/10 | 1000 | 1015
TSK-0141 | PRJ-007 | Network Security Overhaul | Configure API integration | Procurement | Hassan Fouad | high | DELAYED | 05/06/2024 | 16/06/2024 | 25/06/2024 | 10000 | 11220
TSK-0240 | PRJ-012 | Cloud Migration | Plan user interface | Finance | Rania Gaber | high | Complete | 03-31-2024 | 04-29-2024 | 04-30-2024 | 2500 | 2376
TSK-0166 | PRJ-008 | Office Relocation | Plan quality checklist | Ops | Aya Ibrahim | high | Complete | 2024/04/18 | 2024/04/29 | 2024/05/01 |  | 1656
TSK-0179 | PRJ-009 | Supply Chain Optimization | Audit inventory system | QA | Yasmin Younes | Medium | NOT STARTED | 06-Apr-2024 | 30-Apr-2024 |  | 2000 | 0
TSK-0279 | PRJ-014 | Retail Store Opening | Design inventory system | HR | Farida Younes | Medium | Complete | 14-May-2024 | 07-Jun-2024 | 07-Jun-2024 | 6000 | 5085
TSK-0096 | PRJ-005 | Customer Portal Upgrade | Deploy user interface | MARKETING | Mostafa El-Sayed | Medium | In Progress | 04-06-2024 | 04-16-2024 |  | 1500 | 994
TSK-0098 | PRJ-005 | Customer Portal Upgrade | Migrate marketing collateral | I.T | Dina Mahmoud | M | Behind Schedule | 2024-05-09 | 2024-05-20 | 2024-05-18 | 2500 | 2251
TSK-0251 | PRJ-013 | Brand Refresh Campaign | Configure backup procedure | Q.A. | Reem Gaber | high | Pending | 01-May-2024 | 31-May-2024 |  | 5000 | 0
TSK-0278 | PRJ-014 | Retail Store Opening | Train users on security policy | MARKETING | Hassan Fouad | Med | COMPLETED | 2024/01/13 | 2024/02/01 | 2024/01/30 | 6000 | 4896
TSK-0151 | PRJ-008 | Office Relocation | Migrate onboarding process | Operations | Fady Hosny | HIGH | Not started | 07-Apr-2024 | 28-Apr-2024 |  | 2500 | 0
TSK-0294 | PRJ-015 | Data Center Upgrade | Audit budget report | PROCUREMENT | Farida Zaki | MEDIUM | IN PROGRESS | 16/08/2024 | 05/09/2024 |  | 1000 | 620
TSK-0249 | PRJ-012 | Cloud Migration | Document dashboard | IT | Khaled Younes | LOW | Done | 2024-06-02 | 2024-06-22 | 2024-06-20 | 6000 | 8191
TSK-0021 | PRJ-002 | ERP System Rollout | Test dashboard | Finance | Sherif Hosny | LOW | completed | 03-Sep-2024 | 01-Oct-2024 | 29-Sep-2024 | 2000 | 1434
TSK-0129 | PRJ-007 | Network Security Overhaul | Audit warehouse layout | it | Farida Zaki | medium | Delayed | 05-24-2024 | 06-04-2024 | 06-13-2024 | 2500 | 2532
TSK-0069 | PRJ-004 | Warehouse Automation | Audit dashboard | I.T | Tarek Shawky | HIGH | Completed | 2024/11/18 | 2024/12/08 | 2024/12/10 | 4000 | 3867
TSK-0184 | PRJ-009 | Supply Chain Optimization | Design quality checklist | procurement | Tarek Shawky | H | In Progress | 2024-04-09 | 2024-04-15 |  | 2500 | 1249
TSK-0194 | PRJ-010 | Product Line Expansion | Develop network infrastructure | PROCUREMENT | Rania Gaber | H | DELAYED | 14-Jun-2024 | 20-Jun-2024 | 23-Jun-2024 | 8000 | 11105
TSK-0011 | PRJ-001 | Website Redesign | Deploy marketing collateral | H.R. | Mostafa El-Sayed | HIGH | Done | 2024/07/08 | 2024/07/15 | 2024/07/14 | 1500 | 1984
TSK-0099 | PRJ-005 | Customer Portal Upgrade | Test supplier list | Marketing | Yasmin El-Sayed | medium | Delayed | 05-15-2024 | 06-09-2024 | 06-21-2024 | 4000 | 5388
TSK-0225 | PRJ-011 | HR System Implementation | Plan warehouse layout | marketing | Ziad Abdelrahman | LOW | Delayed | 2024-05-23 | 2024-05-31 | 2024-06-05 | 1500 | 1349
TSK-0178 | PRJ-009 | Supply Chain Optimization | Configure network infrastructure | MARKETING | Hana Zaki | High | Delayed | 28-Apr-2024 | 01-May-2024 | 01-May-2024 | 2000 | 2018
TSK-0286 | PRJ-014 | Retail Store Opening | Procure employee handbook | H.R. | Ziad Abdelrahman | M | Ongoing | 14/04/2024 | 06/05/2024 |  | 3000 | 2385
TSK-0163 | PRJ-008 | Office Relocation | Deploy quality checklist | PROCUREMENT | Hassan Fouad | Medium | completed | 2024-06-28 | 2024-07-04 | 2024-07-03 | 5000 | 6722
TSK-0120 | PRJ-006 | CRM Migration | Deploy server configuration | Operations | Dina Fouad | H | In Progress | 2024-04-17 | 2024-05-03 |  | 8000 | 5320
TSK-0250 | PRJ-012 | Cloud Migration | Analyze vendor contract | HR | Khaled Younes | L | COMPLETED | 02-22-2024 | 02-28-2024 | 03-01-2024 | 2500 | 1754
TSK-0065 | PRJ-003 | Mobile App Launch | Configure budget report | I.T. | Sherif Hosny | Low | not started | 10/03/2024 | 07/04/2024 |  | 4000 | 0
TSK-0055 | PRJ-003 | Mobile App Launch | Approve customer feedback survey | FINANCE | Hassan Fouad | L | in progress | 2024/07/20 | 2024/08/13 |  | 2000 | 604
TSK-0275 | PRJ-014 | Retail Store Opening | Optimize quality checklist | MARKETING | Fady Hosny | low | completed | 22/05/2024 | 29/05/2024 | 29/05/2024 | 2000 | 1651
TSK-0079 | PRJ-004 | Warehouse Automation | Approve server configuration | Finance | Sherif Hosny | H | IN PROGRESS | 22-Sep-2024 | 27-Sep-2024 |  | 5000 | 3533
TSK-0183 | PRJ-009 | Supply Chain Optimization | Audit security policy | MARKETING | Yasmin Zaki | Medium | completed | 2024-03-05 | 2024-03-25 | 2024-03-26 | 10000 | 12048
TSK-0042 | PRJ-003 | Mobile App Launch | Configure supplier list | Finance | Aya Ibrahim | L | IN PROGRESS | 2024/03/16 | 2024/04/09 |  | 2500 | 1886
TSK-0031 | PRJ-002 | ERP System Rollout | Develop quality checklist | Finance | Tarek Shawky | high | in progress | 2024-08-03 | 2024-08-28 |  | 3000 | 2131
TSK-0174 | PRJ-009 | Supply Chain Optimization | Review network infrastructure | Operations | Farida Zaki | M | Done | 2024/05/18 | 2024/05/26 | 2024/05/25 | 3000 | 2708
TSK-0047 | PRJ-003 | Mobile App Launch | Audit dashboard | IT | Farida Hosny | HIGH | Completed | 03/07/2024 | 26/07/2024 | 26/07/2024 | 1000 | 842
TSK-0256 | PRJ-013 | Brand Refresh Campaign | Audit marketing collateral | Quality Assurance | Aya Ibrahim | medium | Completed | 14/04/2024 | 08/05/2024 | 05/05/2024 | 2500 | 2217
TSK-0081 | PRJ-004 | Warehouse Automation | Migrate backup procedure | Operations | Noor Naguib | H | In Progress | 2024/10/18 | 2024/11/14 |  | 10000 | 6559
TSK-0128 | PRJ-007 | Network Security Overhaul | Procure server configuration | Procurement |  | M | NOT STARTED | 11-Jul-2024 | 19-Jul-2024 |  | 10000 | 0
TSK-0046 | PRJ-003 | Mobile App Launch | Review onboarding process | OPERATIONS | Farida Zaki | Med | In Progress | 07-16-2024 | 07-20-2024 |  | 6000 | 1517
TSK-0191 | PRJ-010 | Product Line Expansion | Develop training material | PROCUREMENT | Tarek Abdelrahman | H | IN PROGRESS | 2024/06/17 | 2024/06/28 |  | 1500 | 814
TSK-0080 | PRJ-004 | Warehouse Automation | Deploy inventory system | procurement | Khaled Younes | High | in progress | 11-04-2024 | 11-23-2024 |  | 2500 | 1859
TSK-0306 | PRJ-015 | Data Center Upgrade | Develop database schema | OPERATIONS | Dina Fouad | high | Delayed | 2024/07/16 | 2024/07/22 | 2024/07/22 | 1500 | 2034
TSK-0244 | PRJ-012 | Cloud Migration | Procure warehouse layout | Q.A. | Farida Younes | medium | Complete | 2024-02-21 | 2024-02-28 | 2024-03-01 | 1000 | 1387
TSK-0298 | PRJ-015 | Data Center Upgrade | Design security policy | HR | Sherif Ibrahim | low | Complete | 2024-08-01 | 2024-08-07 | 2024-08-09 | 8000 | 8176
TSK-0022 | PRJ-002 | ERP System Rollout | Install user interface | Ops | Sherif Ibrahim | High | completed | 2024/08/04 | 2024/08/31 | 2024/08/31 | 2500
TSK-0005 | PRJ-001 | Website Redesign | Install employee handbook | Quality Assurance | Sherif Hosny | L | in progress | 2024-07-17 | 2024-08-02 |  | 2000 | 734
TSK-0125 | PRJ-006 | CRM Migration | Migrate hardware setup | it | Dina Mahmoud | H | Pending | 06-25-2024 | 07-13-2024 |  | 2500 | 0
TSK-0203 | PRJ-010 | Product Line Expansion | Document database schema | QA | Khaled Naguib | M | Complete | 2024/08/03 | 2024/08/16 | 2024/08/16 | 3000 | 2478
TSK-0062 | PRJ-003 | Mobile App Launch | Review network infrastructure | IT | Yasmin Zaki | M | Behind Schedule | 23-Apr-2024 | 16-May-2024 | 15-May-2024 | 6000 | 8019
TSK-0300 | PRJ-015 | Data Center Upgrade | Document employee handbook | Q.A. | Mostafa El-Sayed | low | in progress | 08-31-2024 | 09-24-2024 |  | 2500 | 1721
TSK-0142 | PRJ-007 | Network Security Overhaul | Migrate hardware setup | Finance | Ziad Abdelrahman | Low | in progress | 22/09/2024 | 02/10/2024 |  | 10000 | 6223
TSK-0086 | PRJ-004 | Warehouse Automation | Audit employee handbook | hr | Sherif Ibrahim | low | Ongoing | 2024-09-19 | 2024-10-01 |  | 5000 | 1387
TSK-0008 | PRJ-001 | Website Redesign | Approve vendor contract | hr | Mariam Kamal | high | Pending | 29/06/2024 | 21/07/2024 |  | 1500 | 0
TSK-0167 | PRJ-008 | Office Relocation | Plan hardware setup | Finance | Noor Naguib | L | COMPLETED | 2024/06/05 | 2024/06/26 | 2024/06/23 | 4000 | 3786
TSK-0223 | PRJ-011 | HR System Implementation | Design training material | Marketing | Dina Mahmoud | high | COMPLETED | 2024/03/12 | 2024/03/24 | 2024/03/26 | 8000 | 7859
TSK-0129 | PRJ-007 | Network Security Overhaul | Audit warehouse layout | it | Farida Zaki | medium | Delayed | 05-24-2024 | 06-04-2024 | 06-13-2024 | 2500 | 2532
TSK-0121 | PRJ-006 | CRM Migration | Optimize security policy | procurement | Mostafa El-Sayed | H | COMPLETED | 07-10-2024 | 07-23-2024 | 07-24-2024 | 4000 | 4692
Note: this sheet is the RAW export on purpose — inconsistent text, mixed date formats, duplicates, blanks and a few test rows are intentional. Do not edit it; clean it in Power Query.

## PQ_Output
Load your cleaned Power Query output table here (Excel Table: tbl_Tasks_Clean).

## PivotTables
Row Labels | Sum of Planned_Cost | Sum of Actual_Cost
Brand Refresh Campaign | 70000 | 48164
Cloud Migration | 66000 | 49405
CRM Migration | 109500 | 73502
Customer Portal Upgrade | 85500 | 65762
Data Center Upgrade | 90000 | 74295
ERP System Rollout | 97500 | 71644
HR System Implementation | 112000 | 74792
Mobile App Launch | 106000 | 90358
Network Security Overhaul | 110000 | 65885
Office Relocation | 93000 | 74881
Product Line Expansion | 85500 | 46665
Retail Store Opening | 93000 | 58608
Supply Chain Optimization | 74000 | 53913
Warehouse Automation | 78500 | 67742
Website Redesign | 53000 | 38606
Grand Total | 1323500 | 954222
Count of Task_ID | Column Labels
Row Labels | Behind Schedule | Completed | Delayed | Done | In Progress | Not Started | Ongoing | Pending | Grand Total
HR | 1 | 13 | 5 | 3 | 6 | 3 | 5 | 2 | 38
IT | 2 | 19 | 7 | 5 | 8 | 7 | 1 | 2 | 51
Marketing | 1 | 13 | 7 | 4 | 12 | 4 | 6 | 4 | 51
Procurement |  | 13 | 6 | 2 | 16 | 3 | 2 |  | 42
Grand Total | 4 | 58 | 25 | 14 | 42 | 17 | 14 | 8 | 182
Average of Delay_Days | Column Labels
Row Labels | High | Low | Medium | Not Set | Grand Total
HR | 2.7692 | 0.54545 | 0.33333 | 0 | 1.2105
IT | 0.04 | 0.33333 | 0.53846 | 0 | 0.23529
Marketing | 0.26667 | 0.25 | 1.3 |  | 0.66667
Procurement | 0.14286 | -0.13333 | 1.1667 | 0 | 0.33333
Grand Total | 0.64179 | 0.22222 | 0.89474 | 0 | 0.58242
Row Labels | Sum of Actual_Cost
Hassan Fouad | 65635
Khaled Naguib | 47894
Noor Naguib | 64193
Sherif Ibrahim | 58857
Tarek Shawky | 49862
Grand Total | 286441
Column Labels
| (blank) |  |  |  | Finance |  |  |  | HR |  |  |  | IT |  |  |  | Marketing |  |  |  | Operations |  |  |  | Procurement |  |  |  | Quality |  |  |  | Total Total Planned Cost | Total Total Actual Cost | Total Cost Variance % | Total On-Time Completion Rate
Row Labels | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate | Total Planned Cost | Total Actual Cost | Cost Variance % | On-Time Completion Rate
Brand Refresh Campaign |  |  |  |  | 5000 | 0 | -100% |  | 6500 | 6582 | 1.262% |  | 14000 | 10857 | -22.45% | 0.5 | 7000 | 993 | -85.81% |  | 11500 | 9106 | -20.82% |  | 2500 | 2920 | 16.8% | 1 | 23500 | 17706 | -24.66% | 0.66667 | 70000 | 48164 | -31.19% | 0.66667
Cloud Migration |  |  |  |  | 7000 | 7008 | 0.1143% | 0.66667 | 10500 | 6217 | -40.79% |  | 12000 | 10972 | -8.567% | 1 | 6000 | 5191 | -13.48% | 1 | 3500 | 3415 | -2.429% |  | 18000 | 8910 | -50.5% |  | 9000 | 7692 | -14.53% |  | 66000 | 49405 | -25.14% | 0.57143
CRM Migration | 3000 | 0 | -1 |  | 7000 | 5101 | -27.13% |  | 14000 | 5228 | -62.66% | 1 | 12500 | 5055 | -59.56% |  | 13000 | 10243 | -21.21% |  | 29000 | 17745 | -38.81% |  | 15000 | 9816 | -34.56% |  | 16000 | 20314 | 26.96% |  | 109500 | 73502 | -32.87% | 0.25
Customer Portal Upgrade | 10000 | 0 | -1 |  | 15500 | 17043 | 9.955% | 1 |  |  |  |  | 8500 | 5599 | -34.13% |  | 34500 | 28804 | -16.51% | 1 |  |  |  |  | 1500 | 1802 | 20.13% | 1 | 15500 | 12514 | -19.26% | 1 | 85500 | 65762 | -23.09% | 1
Data Center Upgrade |  |  |  |  | 31500 | 18153 | -42.37% | 1 | 8000 | 8176 | 2.2% |  | 8500 | 9783 | 15.09% | 1 | 10500 | 6214 | -40.82% |  | 17500 | 20753 | 18.59% |  | 9500 | 7094 | -25.33% |  | 4500 | 4122 | -8.4% | 1 | 90000 | 74295 | -17.45% | 0.57143
ERP System Rollout | 10000 | 5205 | -0.4795 |  | 9500 | 7948 | -16.34% | 1 |  |  |  |  | 29000 | 22160 | -23.59% | 1 | 5500 | 551 | -89.98% |  | 16000 | 10087 | -36.96% | 1 | 22500 | 19206 | -14.64% | 0.5 | 5000 | 6487 | 29.74% |  | 97500 | 71644 | -26.52% | 0.85714
HR System Implementation |  |  |  |  | 11000 | 6201 | -43.63% |  | 9000 | 2904 | -67.73% |  | 15000 | 6612 | -55.92% |  | 41500 | 33192 | -20.02% |  | 11500 | 14011 | 21.83% | 0.66667 | 20000 | 9096 | -54.52% |  | 4000 | 2776 | -30.6% |  | 112000 | 74792 | -33.22% | 0.5
Mobile App Launch | 1000 | 0 | -1 |  | 4500 | 2490 | -44.67% |  | 21000 | 17646 | -15.97% | 1 | 18000 | 16850 | -6.389% | 0.75 | 18000 | 11059 | -38.56% |  | 25000 | 26903 | 7.612% | 0.33333 | 10500 | 9118 | -13.16% | 1 | 8000 | 6292 | -21.35% |  | 106000 | 90358 | -14.76% | 0.76923
Network Security Overhaul |  |  |  |  | 22000 | 15511 | -29.5% |  | 6000 | 1369 | -77.18% |  | 12000 | 12132 | 1.1% | 1 | 2500 | 0 | -100% |  | 36000 | 20671 | -42.58% | 0.5 | 30000 | 14584 | -51.39% | 1 | 1500 | 1618 | 7.867% |  | 110000 | 65885 | -40.1% | 0.8
Office Relocation | 10000 | 5964 | -0.4036 |  | 13000 | 13468 | 3.6% | 1 | 25000 | 24201 | -3.196% | 0.5 | 3000 | 2732 | -8.933% |  | 17000 | 7762 | -54.34% |  | 9500 | 8051 | -15.25% | 0.66667 | 6500 | 6722 | 3.415% | 1 | 9000 | 5981 | -33.54% | 1 | 93000 | 74881 | -19.48% | 0.75
Product Line Expansion |  |  |  |  | 7000 | 3074 | -56.09% |  | 16500 | 8612 | -47.81% | 1 | 22500 | 12070 | -46.36% | 0.66667 |  |  |  |  | 11000 | 3262 | -70.35% |  | 17500 | 17169 | -1.891% |  | 11000 | 2478 | -77.47% | 1 | 85500 | 46665 | -45.42% | 0.83333
Retail Store Opening |  |  |  |  | 22000 | 17548 | -20.24% | 1 | 19000 | 15938 | -16.12% | 1 | 10000 | 2591 | -74.09% | 0.5 | 21000 | 11903 | -43.32% | 1 | 15000 | 4270 | -71.53% | 1 | 4000 | 4446 | 11.15% | 1 | 2000 | 1912 | -4.4% | 1 | 93000 | 58608 | -36.98% | 0.90909
Supply Chain Optimization | 1500 | 312 | -0.792 |  | 5000 | 2255 | -54.9% |  | 3000 | 742 | -75.27% |  | 8500 | 4316 | -49.22% |  | 18000 | 22257 | 23.65% | 0.5 | 16000 | 8693 | -45.67% |  | 14500 | 10648 | -26.57% | 1 | 7500 | 4690 | -37.47% | 1 | 74000 | 53913 | -27.14% | 0.75
Warehouse Automation |  |  |  |  | 10000 | 7841 | -21.59% |  | 6500 | 1387 | -78.66% |  | 16000 | 17338 | 8.363% | 0.33333 | 15500 | 15105 | -2.548% | 0.5 | 10000 | 6559 | -34.41% |  | 11500 | 11161 | -2.948% | 1 | 9000 | 8351 | -7.211% |  | 78500 | 67742 | -13.7% | 0.5
Website Redesign |  |  |  |  | 8000 | 6790 | -15.12% | 1 | 15000 | 14941 | -0.3933% | 1 | 6000 | 5586 | -6.9% |  | 8000 | 3393 | -57.59% |  | 1500 | 618 | -58.8% |  | 5500 | 2641 | -51.98% |  | 9000 | 4637 | -48.48% |  | 53000 | 38606 | -27.16% | 1
Grand Total | 35500 | 11481 | -0.67659 |  | 178000 | 130431 | -0.26724 | 0.92308 | 160000 | 113943 | -0.28786 | 0.76923 | 195500 | 144653 | -0.26009 | 0.68421 | 218000 | 156667 | -0.28134 | 0.61538 | 213000 | 154144 | -0.27632 | 0.5625 | 189000 | 135333 | -0.28395 | 0.84615 | 134500 | 107570 | -0.20022 | 0.81818 | 1323500 | 954222 | -0.27902 | 0.73469
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard
PMO Project Analytics Dashboard
Total Planned Cost | Total Actual Cost | Cost Variance % | On-Tme Completion Rate
1323500 | 954222 | -27.9% | 73.47%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.